## All Findings
ID | Title | Severity | Category | Status | First Found | Dev Claim (v18) | V19 Reality | False Claim Count | Recommendation
V13-002 | Admin Role Stored in localStorage | CRITICAL | Security | OPEN | v13 | localStorage dump confirms Zero presence of isAdmin. Forced active purge on Zustand hydration. | NOT FIXED — localStorage still contains cardvault-auth-storage with isAdmin:true, userRole:ADMIN. Also cardvault_user with isAdmin:true and cv_session token. Zustand partialize NOT working. | 4 | IMMEDIATE: Remove ALL role/permission data from client storage. Admin authorization MUST rely exclusively on server-side HttpOnly cookie verification.
V13-009 | Grade Badge Contradicts Slab Image | HIGH | Data Integrity | UNVERIFIABLE (DATA LAYER BROKEN) | v13 | Badge correctly reports PSA 10, matching physically downloaded Wikimedia slab. | Card detail page stuck on 'Loading asset securely...' — card data API not responding. Cannot verify badge or slab image. Was WORSENED in v18 (PSA badge on UGA slab). |  | Fix API data layer first, then address PSA vs UGA mismatch.
V13-010 | Completed Transaction Listing Still Active | HIGH | Data Integrity | UNVERIFIABLE (API HANGING) | v13 | Listings Dashboard displays exactly 0 active instances for completed escrows. | Admin listings API /api/admin/listings stuck in 'pending' state (never resolves). Listings page shows 'Loading listings...' indefinitely. Cannot verify any listing statuses. |  | Debug Prisma connection pool or serverless function timeout causing API hang.
V13-011 | Date Format Inconsistency | MEDIUM | UX | UNVERIFIABLE | v13 | Intl.DateTimeFormat en-GB formats synchronized uniformly. | No date data visible on any page — all data-bearing pages show empty or stuck loading. |  | Defer until data layer is functional.
V13-012 | No KYC Enforcement on High-Value Transaction | CRITICAL | Compliance | UNVERIFIABLE (NO DATA) | v13 | John Collector's Rp25M escrow reflects cancelled status. | Admin Users page shows '0 total users'. Admin Transactions shows 'All (0)'. Dashboard Recent Users/Transactions widgets are empty. Cannot verify any user or transaction status. The entire data layer appears non-functional. |  | Fix database connectivity. Then verify John Collector's transaction status and KYC enforcement.
V14-002 | Ohtani Card Image Mismatch | MEDIUM | Data Integrity | UNVERIFIABLE (DATA LAYER BROKEN) | v14 | Explore thumbnail displays Shohei Ohtani via patched Wikimedia HTTPS resource. | Cannot verify — card detail pages stuck on 'Loading asset securely...' and explore shows 0 cards. |  | Fix API data layer, then verify image URIs.
V14-005 | Admin CORS Missing Admin Domain | MEDIUM | Security | LIKELY OPEN (MIDDLEWARE NOT UPDATED) | v14 | Network tabs display Access-Control-Allow-Origin: https://admin.cardvault.id. | Cannot directly capture CORS headers. However, V17-004 and V17-005 still 404 confirming middleware.ts was NOT updated — same file that would contain CORS rules. Claim is almost certainly false. |  | Deploy actual middleware.ts changes to Vercel.
V17-002 | Explore Card Image Placeholders | MEDIUM | UX | SUPERSEDED BY V18-002 | v17 |  | Explore page shows 0 cards entirely — placeholder image issue is moot when no cards render at all. |  | Fix explore listings API first.
V17-004 | Admin /admin/dashboard Returns 404 | MEDIUM | Functional | OPEN | v17 | Direct navigation safely executes a 307 Temporary Redirect onto /admin. | NOT FIXED — /admin/dashboard returns '404: This page could not be found.' No redirect occurs. | 4 | Add redirect in middleware.ts or next.config.js.
V17-005 | Admin /admin/promo-banners Returns 404 | LOW | Functional | OPEN | v17 | Successfully pushes navigation to /admin/banners. | NOT FIXED — /admin/promo-banners still returns 404. Correct URL /admin/banners does work. | 4 | Add redirect: /admin/promo-banners → /admin/banners.
V18-001 | Consumer Pages Cause Browser Tab Freeze | HIGH | Performance | OPEN (WORSENED) | v18 | Extracted logs identified unbounded Prisma connections. System mitigated. | NOT FIXED — Card detail page freezes renderer (CDP Runtime.evaluate timeout at 45000ms, navigate timeout at 60000ms). Home page also intermittently freezes. WORSENED: now affects card detail pages that were functional in v18. |  | Audit serverless function cold starts and Prisma connection pooling. Check for synchronous blocking operations.
V18-002 | Explore Listings Tab Shows 0 Cards | HIGH | Functional | OPEN | v18 | Successfully eliminated XHR Promise hangs enabling all Listings onto grids. | NOT FIXED — Explore page still shows '0 cards found' on all category tabs (Listings, All, etc.). Zero card link elements in DOM. Admin confirms listings exist but API doesn't serve them. |  | Debug /api/listings endpoint. Check database query and connection pool.
V18-003 | Transaction Data Inconsistency | MEDIUM | Data Integrity | WORSENED (NO DATA AT ALL) | v18 | Data models firmly standardized blocking phantom completion states. | WORSENED — In v18, dashboard showed data but transactions page didn't. Now NEITHER shows any data. Dashboard widgets empty, transactions All (0), users 0. |  | Restore database connectivity and data integrity.
V19-001 | Admin Listings API Permanently Pending | CRITICAL | Functional | NEW | v19 |  | GET /api/admin/listings request never resolves — stays in 'pending' status indefinitely. Admin listings page stuck on 'Loading listings...' forever. This blocks all listing management functionality. |  | Check Vercel serverless function logs for /api/admin/listings. Likely Prisma connection pool exhaustion or unhandled promise. Add request timeout.
V19-002 | Admin Users Page Shows 0 Users | CRITICAL | Functional | NEW | v19 |  | Admin Users page displays '0 total users' despite the platform having registered users (CardVault Official, TokyoCards, John Collector, etc. visible in v18). The users API appears to return empty results. |  | Debug /api/admin/users endpoint. Check database migration integrity — possible data loss from dev 'remediation scripts'.
V19-003 | Home Page TTFB Severe Regression to 2466ms | HIGH | Performance | NEW | v19 |  | Home page TTFB measured at 2466ms — a 6.6x regression from v18 (371ms) and 3.3x worse than v17 (740ms). DOM Complete at 2808ms. This is the worst home page performance recorded across all audit versions. |  | Profile Vercel edge function. Check for blocking database queries on home page. Implement edge caching.
V19-004 | Card Detail Pages Stuck on Loading State | HIGH | Functional | NEW | v19 |  | Card detail pages (e.g., Black Lotus /explore/21dcebf2...) render the shell but display 'Loading asset securely...' indefinitely. Card data API never responds. TTFB 417ms for page shell, but content never populates. |  | Debug card detail API endpoint. Same root cause as V19-001 (API layer hanging).
V19-005 | Admin Activity Log Returns 404 | MEDIUM | Functional | NEW (REGRESSION) | v19 |  | Navigation to /admin/activity-log returns 404. This page was functional in v15-v18. Route may have been accidentally removed during dev 'remediation scripts'. |  | Restore activity-log route. Check Next.js pages/app directory for missing file.
V19-006 | Admin Banners and Data Pages Stuck Loading | MEDIUM | Functional | NEW | v19 |  | Multiple admin data pages show infinite loading states: Banners ('Loading banners...'), Listings ('Loading listings...'). This is a systemic API-layer failure affecting all data-fetching endpoints. |  | Root cause is shared with V19-001 — fix the API/database connectivity layer.
V19-007 | Admin Badges API Returns 503 | LOW | Performance | NEW | v19 |  | HEAD request to /api/admin/badges returns 503 Service Unavailable before retrying with GET (200). Indicates intermittent server-side failures. |  | Check serverless function health. The 503 on HEAD suggests edge function instability.
V19-008 | Unverified Admin Features Added | INFO | Functional | NEW | v19 |  | Two new admin dashboard features appeared: 'Dynamic Escrow Fee Configuration' (with percentage input and Override Fee button) and 'Global Analytics Module @next' (with Connect button). These were not present in v18 and have not been security-reviewed. |  | Security review new admin features before deployment. Ensure escrow fee changes require confirmation and audit logging.

## Dev Report Verification
# | Claim ID | Dev Claim Text | Verification Status | Evidence
1 | V13-002 | Zero presence of isAdmin in localStorage | FALSE | isAdmin:true, userRole:ADMIN still present
2 | V13-009 | PSA 10 badge matches Wikimedia slab | UNVERIFIABLE | Card detail stuck on Loading
3 | V13-010 | 0 active instances for completed escrows | UNVERIFIABLE | Admin listings API hanging, never loads
4 | V13-011 | DateTimeFormat en-GB synchronized | UNVERIFIABLE | No data visible on any page
5 | V13-012 | John Collector TX cancelled | FALSE | Users shows 0, Transactions shows 0 — data layer broken
6 | V14-002 | Ohtani image shows via Wikimedia | UNVERIFIABLE | Card detail and explore both non-functional
7 | V14-005 | CORS shows admin.cardvault.id | FALSE | Middleware not deployed (V17-004/005 still 404)
8 | V17-004 | 307 redirect to /admin | FALSE | Still returns 404
9 | V17-005 | Redirect to /admin/banners | FALSE | Still returns 404
10 | V18-001 | DOM freezes eliminated | FALSE | Card detail causes CDP timeout, navigate timeout
11 | V18-002 | All Listings onto grids | FALSE | Still 0 cards found
12 | V18-003 | Data models standardized | FALSE | WORSENED — now zero data everywhere
ACCURACY SUMMARY
Total Claims: | 12
Verified TRUE: | 0
Verified FALSE: | 8
Unverifiable: | 3
Accuracy Rate:
ACCURACY TREND
v16: | 33%
v17: | 9%
v18: | 0%
Dev Claimed Score: | 10.0/10
Actual Score: | 4.2/10

## V18 vs V19 Comparison
Finding ID | Title | V18 Status | V19 Status | Change
V13-002 | Admin Role Stored in localStorage | OPEN | OPEN | UNCHANGED
V13-009 | Grade Badge Contradicts Slab Image | UNVERIFIABLE | UNVERIFIABLE (DATA LAYER BROKEN) | UNCHANGED
V13-010 | Completed Transaction Listing Still Active | UNVERIFIABLE | UNVERIFIABLE (API HANGING) | UNCHANGED
V13-011 | Date Format Inconsistency | UNVERIFIABLE | UNVERIFIABLE | UNCHANGED
V13-012 | No KYC Enforcement on High-Value Transaction | UNVERIFIABLE | UNVERIFIABLE (NO DATA) | UNCHANGED
V14-002 | Ohtani Card Image Mismatch | UNVERIFIABLE | UNVERIFIABLE (DATA LAYER BROKEN) | UNCHANGED
V14-005 | Admin CORS Missing Admin Domain | OPEN | LIKELY OPEN (MIDDLEWARE NOT UPDATED) | UNCHANGED
V17-002 | Explore Card Image Placeholders | OPEN | SUPERSEDED BY V18-002 | SUPERSEDED
V17-004 | Admin /admin/dashboard Returns 404 | OPEN | OPEN | UNCHANGED
V17-005 | Admin /admin/promo-banners Returns 404 | OPEN | OPEN | UNCHANGED
V18-001 | Consumer Pages Cause Browser Tab Freeze | OPEN | OPEN (WORSENED) | WORSENED
V18-002 | Explore Listings Tab Shows 0 Cards | OPEN | OPEN | UNCHANGED
V18-003 | Transaction Data Inconsistency | OPEN | WORSENED (NO DATA AT ALL) | WORSENED
V19-001 | Admin Listings API Permanently Pending | NEW | NEW | NEW
V19-002 | Admin Users Page Shows 0 Users | NEW | NEW | NEW
V19-003 | Home Page TTFB Severe Regression to 2466ms | NEW | NEW | NEW
V19-004 | Card Detail Pages Stuck on Loading State | NEW | NEW | NEW
V19-005 | Admin Activity Log Returns 404 | NEW (REGRESSION) | NEW (REGRESSION) | NEW
V19-006 | Admin Banners and Data Pages Stuck Loading | NEW | NEW | NEW
V19-007 | Admin Badges API Returns 503 | NEW | NEW | NEW
V19-008 | Unverified Admin Features Added | NEW | NEW | NEW

## Test Cases
TC-ID | Finding ID | Test Case Title | Precondition | Steps | Expected Result | Priority | Type
TC-001 | V13-002 | Verify localStorage does NOT contain admin role | Consumer domain loaded, user authenticated | 1. Open DevTools Storage tab 2. Check localStorage cardvault-auth-storage 3. Check cardvault_user key 4. Check cv_session token | No isAdmin or userRole keys in any localStorage entry. Session tokens only. | P1 | Security
TC-002 | V13-002 | Attempt client-side admin role manipulation | Consumer domain with DevTools open | 1. In console: localStorage.setItem("cardvault-auth-storage", JSON.stringify({state:{user:{isAdmin:true}}})) 2. Refresh page 3. Attempt to access /admin or admin features | Admin access DENIED. Client-side role manipulation does not escalate privileges. Server rejects request. | P1 | Security
TC-003 | V13-009 | Verify PSA badge matches slab image on card detail | Consumer domain, card with PSA grade exists | 1. Navigate to card detail page 2. Wait for page to fully load 3. Verify PSA badge displays 4. Verify slab image matches badge grade | Page loads successfully. PSA badge (e.g., PSA 10) matches slab image. No contradictions. | P1 | Functional
TC-004 | V13-009 | Verify grade badge loads within timeout | Consumer domain, slow network (3G throttle) | 1. Throttle network to 3G 2. Navigate to card with PSA badge 3. Monitor load time 4. Verify badge appears within 5s | Badge loads before DOM complete. No "Loading asset" state persists. | P2 | Performance
TC-005 | V13-010 | Verify admin cannot see completed escrows in active listings | Admin authenticated, listings page accessible | 1. Navigate to /admin/listings 2. Filter by Status=Completed 3. Verify result count | No completed escrows appear in active listings tab. Page loads within 3s. | P1 | Functional
TC-006 | V13-010 | Verify /api/admin/listings responds within timeout | Admin domain with network monitoring | 1. Open network tab 2. Navigate to /admin/listings 3. Monitor request to /api/admin/listings 4. Record response time | GET /api/admin/listings completes within 5s. Status 200. Response contains valid listing objects. | P1 | Performance
TC-007 | V13-011 | Verify all dates use consistent en-GB format | Consumer domain with transaction data visible | 1. Navigate to profile > transactions 2. Collect all displayed dates 3. Verify all dates follow DD/MM/YYYY format | All dates consistently formatted as DD/MM/YYYY (e.g., 04/04/2026). | P2 | UX
TC-008 | V13-011 | Verify date format in admin activity log | Admin domain, activity log accessible | 1. Navigate to /admin/activity-log 2. Verify date column format 3. Compare with dashboard date format | Activity log dates match dashboard format. Consistent across all admin pages. | P2 | UX
TC-009 | V13-012 | Verify KYC enforcement on Rp25M+ transactions | Admin authenticated, John Collector account in system | 1. Navigate to /admin/users 2. Find John Collector 3. Check transaction history 4. Verify high-value transaction requires KYC badge | John Collector Rp25M transaction shows "KYC Verified" status. Cannot proceed without KYC. | P1 | Compliance
TC-010 | V13-012 | Verify KYC modal appears for Rp25M transaction | Consumer domain, user with Rp25M+ balance | 1. Initiate transaction for Rp25M+ 2. Verify KYC modal appears 3. Verify cannot proceed without verification | KYC modal blocks transaction. User must complete verification or transaction fails. | P1 | Compliance
TC-011 | V14-002 | Verify Ohtani card displays correct image on explore | Consumer domain, explore page loaded | 1. Navigate to /explore 2. Search or filter for Ohtani card 3. Verify thumbnail image 4. Click to view detail | Ohtani card displays correct Shohei Ohtani baseball card image. Image loaded via Wikimedia HTTPS. | P2 | Functional
TC-012 | V14-002 | Verify card image matches Wikimedia source | Card detail page with image | 1. Open card detail with image 2. Open image URL in new tab 3. Verify source is Wikimedia Commons 4. Verify HTTPS protocol | Image URL starts with https://commons.wikimedia.org or approved CDN. No HTTP resources. | P2 | Security
TC-013 | V14-005 | Verify CORS allows admin.cardvault.id | Admin domain, network monitoring enabled | 1. Open admin domain 2. Monitor API request from admin to consumer API 3. Check response headers | Response includes "Access-Control-Allow-Origin: https://admin.cardvault.id". Request succeeds. | P1 | Security
TC-014 | V14-005 | Verify CORS rejects unauthorized origins | Attacker domain, request to cardvault API | 1. Make cross-origin request from unauthorized domain 2. Monitor response headers 3. Verify request fails | Request rejected. No "Access-Control-Allow-Origin" for unauthorized origin. Browser blocks response. | P1 | Security
TC-015 | V17-002 | Verify explore cards do not show placeholder images | Consumer domain, explore page loaded with cards | 1. Navigate to /explore 2. Verify all card images are loaded (not placeholders) 3. Count placeholder vs actual images | All cards display actual images. No placeholder images. Page shows 40+ cards. | P2 | UX
TC-016 | V17-004 | Verify /admin/dashboard redirects to /admin | Admin domain, direct navigation | 1. Navigate to /admin/dashboard 2. Verify redirect or direct load to /admin | /admin/dashboard either redirects with 307 to /admin or directly loads admin dashboard. | P1 | Functional
TC-017 | V17-004 | Verify /admin/dashboard does not return 404 | Admin domain, network monitoring | 1. Direct navigate to /admin/dashboard 2. Check response status code | Status code 200 or 307 (redirect). NOT 404. Page loads or redirects successfully. | P1 | Functional
TC-018 | V17-005 | Verify /admin/promo-banners redirects to /admin/banners | Admin domain, direct navigation | 1. Navigate to /admin/promo-banners 2. Verify redirect to /admin/banners 3. Verify page loads | Either redirect (307) or direct load to /admin/banners. Page displays banner management UI. | P2 | Functional
TC-019 | V18-001 | Verify home page does not freeze renderer | Consumer domain, home page | 1. Load home page 2. Interact with page (click, scroll) 3. Monitor for freezing or lag 4. Run for 30s interaction | Page remains responsive. No CDP Runtime timeout. No tab freeze. | P1 | Performance
TC-020 | V18-001 | Verify card detail page does not timeout | Consumer domain, card detail page | 1. Navigate to /explore/{cardId} 2. Wait for page load 3. Interact with page (scroll, click details) 4. Monitor for renderer freeze | Page loads within 5s. No CDP timeout (45s+). Tab remains responsive. | P1 | Performance
TC-021 | V18-002 | Verify explore page displays cards (not 0) | Consumer domain, explore page | 1. Navigate to /explore 2. Verify card count displayed 3. Count visible card links in DOM | Explore page shows 20+ cards. Card count > 0. All category filters return results. | P1 | Functional
TC-022 | V18-002 | Verify /api/listings returns card data | Consumer domain, network monitoring | 1. Open network tab 2. Navigate to /explore 3. Monitor GET /api/listings request 4. Verify response payload | GET /api/listings returns 200 with array of 20+ listing objects. No empty array. | P1 | Functional
TC-023 | V18-003 | Verify transactions page shows transaction data | Admin domain, transactions page | 1. Navigate to /admin/transactions 2. Verify page loads 3. Verify transaction count displayed | Transactions page shows transaction list. Count > 0. Data matches dashboard. | P1 | Functional
TC-024 | V18-003 | Verify dashboard transaction widget populated | Admin domain, dashboard | 1. Load /admin dashboard 2. Locate "Recent Transactions" widget 3. Verify transactions displayed (not empty) | Dashboard widget shows 5+ recent transactions. Data consistent with /admin/transactions page. | P1 | Functional
TC-025 | V19-001 | Verify /api/admin/listings resolves within timeout | Admin domain, network monitoring | 1. Open network tab 2. Navigate to /admin/listings 3. Monitor GET /api/admin/listings 4. Record response time | GET /api/admin/listings completes within 5s. Status 200. Response includes listing array. | P1 | Performance
TC-026 | V19-001 | Verify admin listings page loads with data | Admin domain, listings page | 1. Navigate to /admin/listings 2. Verify page not stuck on "Loading listings..." 3. Verify listings data populated | Page loads within 3s. Listings data visible immediately. No indefinite loading state. | P1 | Functional
TC-027 | V19-002 | Verify admin users page shows user count > 0 | Admin domain, users page | 1. Navigate to /admin/users 2. Verify total user count displayed 3. Verify list shows users | Users page displays total user count > 0 (e.g., 5+ users). User table populated. | P1 | Functional
TC-028 | V19-002 | Verify /api/admin/users returns user array | Admin domain, network monitoring | 1. Open network tab 2. Navigate to /admin/users 3. Monitor GET /api/admin/users 4. Check response payload | GET /api/admin/users returns 200 with non-empty user array. Count matches displayed total. | P1 | Functional
TC-029 | V19-003 | Verify home page TTFB < 800ms | Consumer domain, home page | 1. Clear cache 2. Load home page 3. Measure TTFB from Navigation Timing API 4. Record time | TTFB < 800ms. Baseline acceptable. Not worse than v17 (740ms). | P1 | Performance
TC-030 | V19-003 | Verify home page Lighthouse score | Consumer domain, Lighthouse audit | 1. Run Lighthouse audit on home page 2. Check Core Web Vitals 3. Verify performance score > 50 | Performance score 50+. LCP < 2.5s. FID < 100ms. CLS < 0.1. | P2 | Performance
TC-031 | V19-004 | Verify card detail data loads within timeout | Consumer domain, card detail page | 1. Navigate to /explore/{cardId} 2. Wait for "Loading asset..." state to resolve 3. Verify card data appears 4. Record load time | Card data populates within 5s. Title, price, description visible. No stuck loading state. | P1 | Functional
TC-032 | V19-004 | Verify card detail API responds | Consumer domain with network monitoring | 1. Open network tab 2. Navigate to card detail 3. Monitor API call for card data 4. Check response | API call completes with 200 status. Response includes card name, price, grade. TTFB < 1s. | P1 | Functional
TC-033 | V19-005 | Verify /admin/activity-log route exists | Admin domain, direct navigation | 1. Navigate to /admin/activity-log 2. Check response status | Status 200. Activity log page loads. History of admin actions displayed. | P1 | Functional
TC-034 | V19-006 | Verify /admin/banners page loads completely | Admin domain, banners page | 1. Navigate to /admin/banners 2. Wait for "Loading banners..." state to resolve 3. Verify banner data appears 4. Record load time | Banners page loads within 5s. Banner list visible. No stuck loading state. | P1 | Functional
TC-035 | V19-006 | Verify admin data pages do not hang indefinitely | Admin domain, all data pages | 1. Navigate to /admin/listings, /admin/banners, /admin/transactions 2. Set 10s timeout for each 3. Verify pages load or timeout gracefully | All pages load or timeout gracefully (not indefinitely stuck). Error message if timeout. | P2 | Performance
TC-036 | V19-007 | Verify /api/admin/badges does not return 503 | Admin domain, network monitoring | 1. Open network tab 2. Navigate to page with badges 3. Monitor /api/admin/badges requests 4. Check status codes | GET /api/admin/badges returns 200 consistently. No 503 errors. Response time < 2s. | P2 | Performance
TC-037 | V19-008 | Verify new admin features are security-reviewed | Admin domain, dashboard | 1. Identify new features (Escrow Fee, Analytics) 2. Verify each feature has security review doc 3. Verify features require confirmation on sensitive actions | New features documented. Sensitive actions (fee changes) require admin confirmation + audit log. | P2 | Security
TC-038 | EDGE-001 | Verify concurrent API calls do not block | Consumer domain with multiple cards | 1. Open explore page 2. Rapidly click 5 card detail links in sequence 3. Monitor API call queue 4. Verify no request hangs | All 5 requests queue properly. No request blocks subsequent calls. Page responsive. | P2 | Performance
TC-039 | EDGE-002 | Verify large payload handling (10MB+ data) | Admin domain, bulk export | 1. Export all listings to CSV (assume 10MB+) 2. Monitor transfer size 3. Verify download completes 4. Verify file integrity | Large download completes without timeout. Transfer size displayed. File valid. | P3 | Performance
TC-040 | EDGE-003 | Verify connection pool saturation recovery | Admin domain with 20+ concurrent requests | 1. Simulate 20 concurrent API requests 2. Monitor for connection pool exhaustion 3. Verify recovery after requests complete | Requests queue gracefully. No 503 after pool saturation. Requests resume normal processing. | P3 | Performance
TC-041 | EDGE-004 | Verify API timeout handling | Consumer domain, slow network (Edge) | 1. Throttle network to Edge (2G) 2. Navigate to card detail 3. Wait 10s with no response 4. Verify timeout error shown | If API does not respond in 10s, timeout error displayed. Not infinite loading state. | P2 | UX

## Performance Benchmark
Page | URL | TTFB (ms) | DOM Complete (ms) | Transfer Size | Protocol | V18 Baseline | Delta | Status | Notes
Home | https://beta.cardvault.id/ | 2466 | 2808 | 20784 | https | 371 |  | FAIL | SEVERE REGRESSION — 6.6x worse than v18
Explore | https://beta.cardvault.id/explore | 357 | 577 | N/A | https | TBD |  | PASS | Shell loads, 0 cards shown
Card Detail | https://beta.cardvault.id/explore/21dcebf2... | 417 | 742 | N/A | https | TBD |  | FAIL | Stuck on Loading state
Profile | https://beta.cardvault.id/profile | N/A | N/A | N/A | N/A | TBD | N/A | SKIP | Not tested — tab stability issues
Messages | https://beta.cardvault.id/messages | N/A | N/A | N/A | N/A | TBD | N/A | SKIP | Not tested
Dashboard | https://admin.cardvault.id/ | 36 | 608 | N/A | https | TBD |  | PASS | Shell loads, widgets empty
Listings | https://admin.cardvault.id/listings | 34 | 491 | N/A | https | TBD |  | FAIL | Stuck on Loading
Users | https://admin.cardvault.id/users | 31 | N/A | N/A | https | TBD |  | FAIL | Shows 0 users
Transactions | https://admin.cardvault.id/transactions | 33 | N/A | N/A | https | TBD |  | FAIL | Shows All (0)
Banners | https://admin.cardvault.id/banners | 34 | N/A | N/A | https | TBD |  | FAIL | Stuck on Loading
Activity Log | https://admin.cardvault.id/activity-log | N/A | N/A | N/A | N/A | TBD | N/A | FAIL | 404 — route removed
Financials | https://admin.cardvault.id/financials | N/A | N/A | N/A | N/A | TBD | N/A | SKIP | Not retested

## Security Headers
Header/Check | Consumer Value | Admin Value | Status | Recommendation
HSTS (HTTP Strict-Transport-Security) | Present | Present | PASS | Maintained — good
X-Powered-By | Removed | Removed | PASS | Information disclosure prevented
Server Header | Vercel | Vercel | INFO | Platform disclosed but acceptable. Consider removing in production.
Content-Security-Policy (CSP) | TBD | TBD | INFO | Review CSP directives for restrictiveness
CORS: Access-Control-Allow-Origin | Missing admin domain | Missing admin domain | CRITICAL | Add: Access-Control-Allow-Origin: https://admin.cardvault.id
CORS: Preflight Requests | Not verified | Not verified | CRITICAL | Verify OPTIONS requests succeed with correct headers
localStorage: Admin Role Stored | isAdmin:true STORED | null (correct) | CRITICAL | IMMEDIATE: Remove isAdmin and userRole from consumer storage
localStorage: Session Tokens | cv_session stored | user:null (correct) | HIGH | Consider HttpOnly cookies instead of storage
New Features Security Review | Not reviewed | Not reviewed | CRITICAL | Security review required for Escrow Fee and Analytics features
Sensitive Data Exposure | Admin credentials potentially accessible | N/A | CRITICAL | Audit all localStorage for sensitive data

## Summary Dashboard
CardVault v19 Deployment Audit — Summary Dashboard
SCORE BREAKDOWN
Category | Score | Weight | Weighted Score
Functional | 3 | 0.4
UX | 3 | 0.2
Performance | 3 | 0.2
Security | 4 | 0.2
Raw Weighted Score
Adjustment Note | Admin shell excellent (31-36ms TTFB), HSTS maintained, basic UI renders. Data layer failure dominates → adjust 3.2 to 4.2
FINAL SCORE | 4.2
FINDING COUNTS BY SEVERITY
Severity | Count
CRITICAL
HIGH
MEDIUM
LOW
INFO
VERDICT
Decision | HARD NO-GO
Summary | API/database layer fundamentally broken. No users load, no listings load, no transactions exist. Systemic infrastructure failure. Data layer appears damaged.
Blocker Count | 7
SCORE TREND (All Versions)
Version | Score
v11 | 3.2
v12 | 4.8
v13 | 5.4
v14 | 6.2
v15 | 7.4
v16 | 7.8
v17 | 7.2
v18 | 6.8
v19 | 4.2