## Security Findings
ID | Title | Severity | OWASP Category | Site | Description | Impact | Remediation | Status | Assigned To | Due Date
SEC-001 | Admin Panel No Authentication | CRITICAL | A01: Broken Access Control | admin.cardvault.id | Entire admin panel accessible without login. Dashboard, Users, Transactions, Listings, Financials, Disputes all publicly accessible. Anyone can view user PII, emails, KYC statuses, transaction amounts, and platform financial data. | Complete platform data exposure. Regulatory and legal liability. User trust destruction. | Implement server-side authentication middleware on ALL admin routes. Add admin login page with email/password + MFA. Validate session token on every API request. Return 401 for unauthenticated requests. | OPEN | Dev Team | Before Deployment
SEC-002 | Missing HSTS on Beta | HIGH | A02: Cryptographic Failures | beta.cardvault.id | Strict-Transport-Security header is missing from beta site API responses. Admin has it correctly configured with max-age=31536000; includeSubDomains; preload. | Users could be subject to SSL stripping/downgrade attacks on initial connection. | Add HSTS header matching admin config: Strict-Transport-Security: max-age=31536000; includeSubDomains; preload | OPEN | DevOps | Before Deployment
SEC-003 | Admin API Endpoints Unauthenticated | CRITICAL | A01: Broken Access Control | admin.cardvault.id | /api/transactions returns 200 with transaction data, /api/listings returns 200 with all listing data, /api/disputes returns 200 with dispute data — all without any authentication token or session cookie. | Direct data exfiltration possible via simple curl commands. | Add authentication middleware to ALL API routes. Validate JWT/session token server-side before returning any data. | OPEN | Dev Team | Before Deployment
SEC-004 | Server Version Disclosure | LOW | A05: Security Misconfiguration | admin.cardvault.id | Server: Vercel header exposes hosting provider information. Build version CVOS v0.85.0 shown in footer. | Helps attackers fingerprint the technology stack for targeted attacks. | Remove Server header via Vercel config. Remove build version from production UI. | OPEN | DevOps | Sprint 2
SEC-005 | Inconsistent Auth Behavior | MEDIUM | A01: Broken Access Control | admin.cardvault.id | KYC Approvals page requires OTP verification for PII access (good), but Dashboard, Transactions, Listings, and Financials pages have NO authentication at all. Inconsistent security model. | Suggests auth was partially implemented. Creates false sense of security on protected pages while leaving others wide open. | Implement unified authentication for ALL admin pages. The OTP gate for KYC is good — extend similar protection to all sensitive pages. | OPEN | Dev Team | Before Deployment
SEC-006 | Notification API Excessive 401s | LOW | A05: Security Misconfiguration | beta.cardvault.id | Frontend repeatedly calls /api/notifications (5+ times per session) even for unauthenticated users, generating 401 responses. | Server resource waste. Could mask legitimate auth failures in logs. Potential for log flooding. | Check authentication status in frontend before making notification API calls. Only initiate polling when user is verified authenticated. | OPEN | Frontend Dev | Sprint 1
SEC-007 | HEAD Request Returns 503 | MEDIUM | A05: Security Misconfiguration | beta.cardvault.id | HEAD request to beta.cardvault.id/ returned HTTP 503 Service Unavailable while GET requests work. | Indicates edge function instability. Could affect uptime monitoring that uses HEAD requests. Health checks may fail. | Investigate Vercel edge function configuration. Ensure HEAD requests are handled properly. Test health check endpoints. | OPEN | DevOps | Sprint 1
SEC-008 | Cache-Control on Beta API | LOW | A05: Security Misconfiguration | beta.cardvault.id | Beta API uses "public, max-age=0, must-revalidate" — while "max-age=0" prevents stale content, "public" allows intermediate caching of potentially sensitive API responses. | Proxies or CDN could cache user-specific API responses. | Change to "private, no-cache, no-store, must-revalidate" for authenticated API endpoints (matching admin's configuration). | OPEN | DevOps | Sprint 2

## OWASP Top 10 Checklist
OWASP ID | Category | Status | Findings | Notes
A01:2021 | Broken Access Control | FAIL | Admin panel completely unauthenticated. API endpoints return data without auth. | CRITICAL - deployment blocker
A02:2021 | Cryptographic Failures | PARTIAL | HSTS missing on beta. HTTPS in use. CSP with nonces present. | Fix HSTS gap
A03:2021 | Injection | PASS | Next.js framework provides default XSS protection. CSP with strict-dynamic. | Continue monitoring
A04:2021 | Insecure Design | PARTIAL | KYC has OTP (good) but inconsistent auth model across admin. No rate limiting observed. | Unify auth model
A05:2021 | Security Misconfiguration | PARTIAL | Server version disclosed. Build version in footer. Inconsistent cache-control. | Multiple low-severity issues
A06:2021 | Vulnerable Components | N/A | Cannot assess without codebase access. Recommend running npm audit. | Run dependency audit
A07:2021 | Auth Failures | FAIL | Admin has no authentication at all for most pages. | CRITICAL
A08:2021 | Data Integrity | N/A | Cannot fully assess without codebase. Check CI/CD pipeline | Check CI/CD pipeline
A09:2021 | Logging Failures | N/A | Cannot assess without server access. | Verify security event logging exists
A10:2021 | SSRF | N/A | Cannot test without codebase access. | Test server-side request handling

## Security Headers
Header | beta.cardvault.id | admin.cardvault.id | Required | Notes
Content-Security-Policy | Present (nonce + strict-dynamic) | Present (nonce + strict-dynamic) | Required | Excellent implementation
X-Frame-Options | DENY | DENY | Required | Prevents clickjacking
X-Content-Type-Options | nosniff | nosniff | Required | Prevents MIME sniffing
Strict-Transport-Security | MISSING | max-age=31536000; includeSubDomains; preload | Required | MUST FIX on beta
X-XSS-Protection | 1; mode=block | 1; mode=block | Recommended | Legacy but helpful
Referrer-Policy | strict-origin-when-cross-origin | strict-origin-when-cross-origin | Recommended | Good
Permissions-Policy | camera=(), microphone=(), geolocation=(), payment=(self) | camera=(), microphone=(), geolocation=(), payment=(self) | Recommended | Good
CORS Access-Control-Allow-Origin | https://beta.cardvault.id | https://beta.cardvault.id | Required | Specific origin (not wildcard) - correct
Cache-Control | public, max-age=0, must-revalidate | private, no-cache, no-store, max-age=0, must-revalidate | Required | Beta should match admin for auth endpoints

## Remediation Roadmap
Phase | ID | Action | Effort | Owner | Status
Phase 1 - Before Deployment | SEC-001 | Implement admin authentication with login + MFA | 3-5 days | Dev Team | REQUIRED
Phase 1 - Before Deployment | SEC-003 | Add auth middleware to all admin API routes | 2-3 days | Dev Team | REQUIRED
Phase 1 - Before Deployment | SEC-002 | Add HSTS header to beta.cardvault.id | 30 mins | DevOps | REQUIRED
Phase 1 - Before Deployment | SEC-005 | Unify auth model across all admin pages | 1-2 days | Dev Team | REQUIRED
Phase 2 - Sprint 1 | SEC-006 | Fix notification API polling for unauth users | 2 hours | Frontend Dev | RECOMMENDED
Phase 2 - Sprint 1 | SEC-007 | Investigate and fix HEAD request 503 | 1 day | DevOps | RECOMMENDED
Phase 3 - Sprint 2 | SEC-004 | Remove server/version information disclosure | 1 hour | DevOps | NICE-TO-HAVE
Phase 3 - Sprint 2 | SEC-008 | Fix cache-control on beta authenticated endpoints | 1 hour | DevOps | NICE-TO-HAVE