## All Findings
ID | Severity | Category | Title | Description | v11 Ref | Status | Recommendation
V12-001 | Critical | Performance | FCP 13,812ms — still 5.5x above 2,500ms target | First Contentful Paint measured at 13,812ms on fresh load. Improved from v11's 16,636ms (-17%) but still massively exceeds the 2,500ms target. The 70% reduction in resources (60→18) hasn't fully translated to FCP improvement, suggesting render-blocking JavaScript in the critical path. | V11-001 | NOT FIXED | Profile the critical rendering path. Identify and defer render-blocking JS. Implement SSR/SSG for the initial HTML shell. Code-split aggressively. Target FCP < 2,500ms.
V12-002 | Critical | Security | Admin role still stored in localStorage — privilege escalation possible | cardvault-auth-storage and cardvault_user in localStorage still contain isAdmin:true and userRole:ADMIN. Plus new cv_session token also stored in localStorage. Any user can modify these via DevTools to gain admin access. | V11-002 | NOT FIXED | Move all auth state to httpOnly cookies. Implement server-side JWT/session-based authorization. Admin endpoints must verify role server-side. Remove client-side role trust.
V12-003 | Critical | Security | Wildcard CORS: Access-Control-Allow-Origin: * on both domains | Both beta.cardvault.id and admin.cardvault.id still return Access-Control-Allow-Origin: *. This allows any website to make requests to CardVault APIs. | V11-003 | NOT FIXED | Restrict CORS to specific origins: ['https://beta.cardvault.id', 'https://admin.cardvault.id']. Configure in Vercel vercel.json or middleware.
V12-004 | Critical | Security | CSP still uses unsafe-eval and unsafe-inline | Content-Security-Policy includes script-src 'unsafe-eval' 'unsafe-inline'. CSP img-src improved (removed http:, now https: only) but core XSS protection still neutered. | V11-004 | PARTIALLY FIXED | Replace unsafe-inline with nonce-based CSP. Eliminate eval() to remove unsafe-eval. Use strict-dynamic.
V12-005 | Critical | Security | HSTS removed from beta.cardvault.id — REGRESSION | Strict-Transport-Security was present on beta.cardvault.id in v11 but is now MISSING. HSTS was added to admin.cardvault.id (previously missing). The consumer-facing app is now vulnerable to SSL stripping attacks. | V11-005 | REGRESSION | Add HSTS to BOTH domains. Ensure Vercel/middleware config applies to all subdomains. Verify with: curl -I https://beta.cardvault.id ¦ grep strict
V12-006 | Critical | Data Integrity | Profile shows '2 Cards' but My Collection shows '0 total cards' | Profile page shows 2 Cards, My Collection sidebar badge shows 2, but My Collection page itself shows '0 total cards' with empty state across all tabs (Collection 0, Listed 0, In Transaction 0, Sold 0). | V11-007 | NOT FIXED | Ensure My Collection queries same data source as Profile. The sidebar badge and Profile stat are correct (2), but the page query returns empty. Debug the /cards or /collection API endpoint.
V12-007 | High | Data Integrity | Grade badge contradicts slab — PSA 9 badge vs GEM MINT 10 on slab | Charizard Base Set Holo: badge shows PSA 9, slab image clearly reads 'PSA GRADED GEM MINT 10'. Additionally, Blue-Eyes White Dragon shows 'BGS 9.5' badge but the slab is from CGC (different grading company entirely). | V11-011 | NOT FIXED | Make grade badges dynamic — read grade value AND company from card data. Map grading company correctly (PSA, BGS, CGC, SGC are all different). Verify against slab image data.
V12-008 | High | UX | Double separator in card subtitle: 'Charizard · · Base Set' | Card detail subtitle shows 'Charizard · · Base Set' because the Year field is empty, creating a double dot separator. | V11-012 | NOT FIXED | Filter empty fields before joining: fields.filter(Boolean).join(' · ')
V12-009 | High | Data Integrity | All listing views counters still show 0 | Admin Listings page shows 0 views for all 4 listings despite pages being visited during testing. | V11-015 | NOT FIXED | Implement view tracking API call on card detail page load. Deduplicate by session/user.
V12-010 | High | Data Integrity | Completed transaction listing still shows 'active' status | Transaction #0906f312 (Rp 25M, John Collector → TokyoCards) is 'Completed' but the associated listing still shows 'active'. The Listings filter now has 'Sold' status option but it's not triggered by completed transactions. | V11-016 | NOT FIXED | Wire transaction completion event to update listing status to 'sold'. Add post-transaction webhook.
V12-011 | High | Data Integrity | Transaction date mismatch across admin pages | Same transaction #0906f312 shows different dates: Transactions page '4/3/2026', Financials page '1 Apr 26', Dashboard 'completed' (no date). These may also be genuinely different dates (April 3 vs April 1). | V11-020 | NOT FIXED | Standardize on one date format (DD MMM YYYY). More critically, verify the actual transaction date is consistent in the database. Create shared formatDate() utility.
V12-012 | High | Security | No KYC enforcement for high-value Rp 25M transaction | John Collector (status: UNVERIFIED) completed a Rp 25,000,000 transaction. KYC verification should be required for transactions above Rp 10,000,000. The buyer was unverified at time of purchase. | V11-027 | NOT FIXED | Implement KYC check in transaction flow. Block transactions > Rp 10M for unverified users. Show verification prompt before checkout.
V12-013 | High | UX | Card title truncation on Explore: 'Shohei Ohtani Chrome R...' | Long card names like 'Shohei Ohtani Chrome RC Auto' are truncated on Explore grid cards without ellipsis tooltip. | V11-025 | NOT FIXED | Add text-overflow: ellipsis with title attribute for tooltip, or allow 2-line wrap for card names.
V12-014 | Medium | Data Integrity | Year field empty, Cert # shows 'N/A' for graded cards | Charizard card detail shows empty Year field and Cert # 'N/A' despite the slab image clearly showing year 1999 and cert number 90001234/73215846. | V11-019 | NOT FIXED | Populate Year and Cert # from grading data. Add these as required fields when condition is 'Graded' in the Sell form.
V12-015 | Medium | Data Integrity | Collection Value 'Rp 0' despite owning listed cards | Profile shows Rp 0 Collection Value. TokyoCards has 2 active listings (Rp 45M + Rp 15.5M = Rp 60.5M) but collection value shows 0. | V11-021 | NOT FIXED | Calculate collection value by summing owned/listed card values.
V12-016 | Medium | UX | '1 trades' grammar error — missing singular form | Profile shows '1 trades' instead of '1 trade'. Appears in both the subtitle and the stats section. | V11-024 | NOT FIXED | count === 1 ? 'trade' : 'trades'. Audit all count labels.
V12-017 | Medium | UX | Dashboard label 'Platform Fees (Revenue)' still ambiguous | Dashboard shows 'PLATFORM FEES (REVENUE)' while Financials correctly separates 'Total Platform Revenue' and 'Gross Volume Processed'. | V11-026 | NOT FIXED | Change to 'Platform Fees' to match Financials page terminology.
V12-018 | Medium | UX | Admin price format inconsistency — commas vs periods | Transactions page shows 'Rp 25,000,000' (comma separators) but Listings and Dashboard show 'Rp 25.000.000' (period separators). Consumer app now uses consistent Rp with periods. | NEW | NEW | Standardize admin panel on period separators to match Indonesian convention and consumer app.
V12-019 | Medium | Performance | /api/home response time regressed 17x — 988ms vs 56ms in v11 | The /api/home endpoint now takes 988ms (just under 1,000ms target) compared to 56ms in v11. This may be due to the endpoint now returning more data or additional processing. At risk of exceeding the 1s target. | NEW (REGRESSION) | REGRESSION | Profile the /api/home endpoint. Add caching layer or optimize database queries. The 56ms achieved in v11 should be the baseline target.
V12-020 | Medium | Performance | /api/notifications called twice on Explore page | Navigating to Explore triggers 2 /api/notifications requests (both returning 401). V11 had reduced this to 1 call. | NEW (REGRESSION) | REGRESSION | Deduplicate notification API calls. Use a request cache or singleton pattern to prevent duplicate calls during SPA navigation.
V12-021 | Medium | Functionality | Bottom nav Explore tab doesn't navigate from Home | Clicking the Explore icon in the bottom navigation bar from the Home page does not navigate to /explore. Direct URL navigation works. SPA routing may be broken for this transition. | NEW | NEW | Debug the onClick handler for the Explore bottom nav link. Check if the Home page layout interferes with the nav click area.
V12-022 | Medium | UX | Chart Y-axis 'Volume (IDR)' without proper Rp formatting | Financials Transaction Volume Trend chart Y-axis label uses 'Volume (IDR)' instead of Rp prefix convention. | V11-028 | NOT FIXED | Format chart axis with 'Rp' prefix. Use abbreviated format for large numbers.
V12-023 | Low | UX | Home page shows no marketplace content — reduced discoverability | Home page was redesigned to show only hero carousel and CTA. No featured cards, featured sellers, or recent listings. While cleaner, this reduces product discoverability for new visitors. | NEW | NEW | Consider adding a 'Recently Listed' or 'Featured Cards' section below the hero to drive engagement. Even 2-3 featured items would improve conversion.
V12-024 | Low | Operations | Build version v0.81 — still not proper semver | Build shows 'CVOS v0.81 © 2026' — improved branding but not standard semantic versioning (MAJOR.MINOR.PATCH). | V11-029 | NOT FIXED | Adopt semver: v0.81.0 or v1.0.0-rc.1 for pre-release. Set up automated versioning in CI/CD.
V12-025 | Low | Functionality | Sell form validation not tested — submit button behavior unknown | Could not fully test form validation in this audit cycle. The Add to Collection button exists but validation behavior on empty required fields needs developer verification. | V11-013 | NEEDS VERIFICATION | Test form submission with empty required fields. Verify inline error messages appear. Ensure form cannot be submitted without required data.

## v11 vs v12 Comparison
v11 ID | Issue | v12 Status | Notes
V11-001 | FCP 16,636ms | IMPROVED | Down to 13,812ms (-17%) but still 5.5x above target
V11-002 | Admin role in localStorage | NOT FIXED | isAdmin:true + new cv_session token still in localStorage
V11-003 | Wildcard CORS * | NOT FIXED | Still Access-Control-Allow-Origin: * on both domains
V11-004 | CSP unsafe-eval/unsafe-inline | PARTIALLY FIXED | img-src fixed (removed http:), but script-src still has unsafe-eval/unsafe-inline
V11-005 | HSTS missing on admin | MIXED | HSTS added to admin BUT removed from beta — net regression
V11-006 | Card detail deep link broken | FIXED | Direct URL navigation now works for card detail pages
V11-007 | Profile vs My Collection mismatch | NOT FIXED | Profile shows 2 Cards, My Collection shows 0 total. Sidebar badge shows 2.
V11-008 | Whitespace void scroll trap | FIXED | docHeight = viewportHeight on Home and Explore. No scrollable void.
V11-009 | No price field on Sell form | FIXED | Price field appears with Rp prefix when 'List for Sale' toggled. Fixed Price + Timed Auction modes.
V11-010 | Compose icon non-functional | FIXED | Opens 'New Direct Message' dialog with recipient search.
V11-011 | Grade badge contradicts slab | NOT FIXED | PSA 9 badge vs GEM MINT 10 slab still present. Plus BGS 9.5 badge on CGC slab.
V11-012 | Double separator · · | NOT FIXED | Still shows 'Charizard · · Base Set'
V11-013 | Sell form no validation feedback | NEEDS VERIFICATION | Form has required field markers. Validation behavior needs testing.
V11-014 | Price format RP vs IDR vs Rp | FIXED | Consumer app now uses consistent 'Rp' with period separators. Admin still has comma/period mix.
V11-015 | All listing views = 0 | NOT FIXED | All 4 listings still show 0 views in admin
V11-016 | Sold listing still active | NOT FIXED | Completed transaction listing still shows 'active'. Filter now has 'Sold' option though.
V11-017 | Trade count contradiction | RESOLVED | Home page redesigned — Featured Sellers section removed. Profile now shows accurate 1 trade.
V11-018 | Vault name truncation | IMPROVED | Card names now better displayed but some truncation remains on long names
V11-019 | Year and Cert # empty | NOT FIXED | Year empty, Cert# shows N/A. Slab shows 1999 and cert numbers.
V11-020 | Date format inconsistency | NOT FIXED | 3 formats: 4/3/2026, 1 Apr 26, 03 Apr. Plus potential date VALUE mismatch.
V11-021 | Collection Value Rp 0 | NOT FIXED | Rp 0 despite 2 listed cards worth Rp 60.5M total
V11-022 | Duplicate empty states | FIXED | My Collection now shows single clean empty state with CTA button.
V11-023 | Filter button 'Apply Requirements' | NOT TESTED | Filter panel not tested in this cycle — needs manual verification
V11-024 | '1 trades' grammar | NOT FIXED | Still shows '1 trades' on Profile page
V11-025 | Card title truncation | NOT FIXED | Shohei Ohtani Chrome R... still truncated
V11-026 | Dashboard revenue label | NOT FIXED | Still 'PLATFORM FEES (REVENUE)'
V11-027 | KYC for high-value tx | NOT FIXED | John Collector UNVERIFIED completed Rp 25M transaction
V11-028 | Chart Y-axis formatting | NOT FIXED | Still 'Volume (IDR)'
V11-029 | Version numbering | IMPROVED | v0.81 with CVOS branding but still not proper semver
V11-030 | Mock listing 404 errors | NOT TESTED | Not specifically tested this cycle

## Test Cases
TC ID | Area | Scenario | Steps | Expected | Priority | Pass/Fail
TC-001 | Performance | Verify FCP on fresh page load | 1. Clear cache and cookies\n2. Open beta.cardvault.id in incognito\n3. Measure FCP via Lighthouse\n4. Record timing | FCP < 2,500ms | Critical
TC-002 | Performance | Verify /api/home response time | 1. Open DevTools Network tab\n2. Navigate to Home\n3. Check /api/home duration | < 500ms (restore v11 baseline of 56ms) | High
TC-003 | Performance | Verify /api/notifications single call | 1. Open DevTools Network\n2. Navigate between pages\n3. Count /api/notifications requests per transition | Exactly 1 call per navigation | Medium
TC-004 | Security | Verify admin role cannot be spoofed via localStorage | 1. Log in as regular user\n2. Set localStorage isAdmin=true, userRole=ADMIN\n3. Refresh\n4. Try admin.cardvault.id/admin | Admin access DENIED. Server returns 403. | Critical
TC-005 | Security | Verify CSP without unsafe directives | 1. Check Content-Security-Policy header\n2. Verify no unsafe-eval or unsafe-inline | Nonce-based CSP. No unsafe-eval/unsafe-inline. | Critical
TC-006 | Security | Verify HSTS on BOTH domains | 1. curl -I https://beta.cardvault.id\n2. curl -I https://admin.cardvault.id\n3. Check Strict-Transport-Security | HSTS present on BOTH with max-age=31536000; includeSubDomains; preload | Critical
TC-007 | Security | Verify CORS not wildcard | 1. Check Access-Control-Allow-Origin header on both domains | Specific origins, NOT * | Critical
TC-008 | Security | Verify KYC for high-value transactions | 1. Create unverified user\n2. Attempt transaction > Rp 10M\n3. Check for KYC gate | Transaction blocked for unverified users above Rp 10M | High
TC-009 | Functionality | Verify card detail deep link | 1. Copy card URL from Explore\n2. Open in new incognito tab\n3. Paste URL and Enter | Card detail loads correctly without redirect | High
TC-010 | Functionality | Verify Sell form price field | 1. Go to Sell/Add Card\n2. Toggle 'List for Sale'\n3. Check for price field\n4. Test Fixed Price and Timed Auction modes | Price field with Rp prefix appears. Both modes functional. | High
TC-011 | Functionality | Verify compose icon on Messages | 1. Go to Messages\n2. Click compose icon\n3. Check for new message dialog | New Direct Message dialog opens with recipient search | High
TC-012 | Functionality | Verify Explore bottom nav works from Home | 1. Go to Home page\n2. Click Explore in bottom nav\n3. Check if /explore loads | Navigates to /explore and shows listings | High
TC-013 | Functionality | Verify Sell form validation | 1. Go to Add New Card\n2. Leave required fields empty\n3. Click Add to Collection\n4. Check for error messages | Inline errors below empty required fields. Form blocked. | High
TC-014 | Data Integrity | Verify Profile card count matches My Collection | 1. Note Profile card count\n2. Go to My Collection\n3. Compare total cards | Both show same count | Critical
TC-015 | Data Integrity | Verify grade badge matches slab | 1. Open each graded card\n2. Compare badge text to slab grade\n3. Compare badge company to slab company | Badge grade AND company match slab exactly | High
TC-016 | Data Integrity | Verify sold listings marked correctly | 1. Complete a transaction\n2. Check listing status in Admin | Status changes from 'active' to 'sold' | High
TC-017 | Data Integrity | Verify listing views increment | 1. Note view count\n2. Visit card detail\n3. Check view count again | View count incremented | High
TC-018 | Data Integrity | Verify transaction date consistency | 1. Check date on Transactions page\n2. Check date on Financials page\n3. Check Dashboard date\n4. Compare all | Same date, same format across all admin pages | High
TC-019 | Data Integrity | Verify Collection Value calculation | 1. Go to Profile\n2. Check Collection Value\n3. Sum all owned card values | Collection Value = sum of card values, not Rp 0 | Medium
TC-020 | Data Integrity | Verify Year and Cert # for graded cards | 1. Open graded card detail\n2. Check Year field\n3. Check Cert # field | Both populated with accurate data from grading cert | Medium
TC-021 | UX | Verify no double separators in card subtitles | 1. Open card with empty Year\n2. Check subtitle format | Clean separators: 'Charizard · Base Set' not 'Charizard · · Base Set' | Medium
TC-022 | UX | Verify singular/plural grammar | 1. Find count = 1 labels\n2. Verify singular form used | '1 trade' not '1 trades' | Medium
TC-023 | UX | Verify consistent currency formatting in admin | 1. Check Transactions page prices\n2. Check Listings page prices\n3. Check Financials page prices | All use 'Rp XX.XXX.XXX' with period separators | Medium
TC-024 | UX | Verify consistent date formatting in admin | 1. Check date format across all admin pages | All use same format: 'DD MMM YYYY' | Medium
TC-025 | UX | Verify card titles not truncated without tooltip | 1. Find card with long name on Explore\n2. Check for truncation\n3. Check for tooltip on hover | Full name visible or truncated with ellipsis+tooltip | Medium
TC-026 | UX | Verify single empty state on My Collection | 1. Go to My Collection with 0 items\n2. Count empty state messages | One empty state message with CTA button | Low
TC-027 | Performance | Verify no whitespace void below content | 1. Scroll to bottom of each page\n2. Check for blank scrollable area | No scrollable whitespace below content | Low
TC-028 | UX | Verify Home page has marketplace content | 1. Navigate to Home\n2. Check for featured cards or recent listings | At least some featured/recent listings to drive engagement | Low

## Performance Benchmark
Page | Metric | v11 Value | v12 Value | Target | Status | Change
Home | FCP | 16,636ms | 13,812ms | < 2,500ms | FAIL | -17%
Home | TTFB | 105ms | 70ms | < 800ms | PASS | -33%
Home | Load Complete | N/A | 250ms | < 3,000ms | PASS | NEW
Home | Resources Loaded | 60 | 18 | < 50 | PASS | -70%
Home | /api/home | 56ms | 988ms | < 1,000ms | NEAR | +1664% REGRESSION
Home | /api/exchange-rate | 335ms | 348ms | < 500ms | PASS | +4%
Home | /api/auth/me | 354ms | 289ms | < 500ms | PASS | -18%
Home | /api/auth/session | 296ms | 275ms | < 500ms | PASS | -7%
Home | /api/notifications | 1 call (316ms) | 1 call (315ms) | 1 call | PASS | Stable
Explore | Direct URL nav | Redirected to / | Loads correctly | Direct access | PASS | FIXED
Explore | /api/listings | N/A | < 1s | < 1,000ms | PASS | NEW endpoint
Explore | /api/notifications calls | 1 | 2 | 1 call | FAIL | REGRESSION
Card Detail | Deep link nav | Redirects to / | Loads correctly | Direct access | PASS | FIXED
Admin Listings | Views counter | 0 (all) | 0 (all) | Accurate counts | FAIL | NOT FIXED

## Security Headers
Header | beta.cardvault.id | admin.cardvault.id | OWASP Recommended | Status
content-security-policy | default-src 'self'; script-src 'self' 'u... | default-src 'self'; script-src 'self' 'u... | No 'unsafe-eval', nonce-based CSP | GOOD
strict-transport-security | MISSING (REGRESSION — was present in v11... | max-age=31536000; includeSubDomains; pre... | max-age=31536000; includeSubDomains; preload | MISSING
permissions-policy | camera=(), microphone=(), geolocation=()... | camera=(), microphone=(), geolocation=()... | Restrict to necessary permissions | GOOD
x-frame-options | DENY | DENY | DENY or SAMEORIGIN | GOOD
x-content-type-options | nosniff | nosniff |  | GOOD
referrer-policy | strict-origin-when-cross-origin | strict-origin-when-cross-origin |  | GOOD
x-xss-protection | 1; mode=block | 1; mode=block |  | GOOD
access-control-allow-origin | * | * | Specific origins, never * | GOOD

## Summary Dashboard
CardVault v12 Audit Summary
Overall Score | 5.2/10 (was 4.2 in v11)
Metrics
Total Findings | 25
Fixed from v11 | 10
New in v12 | 4
Still Open from v11 | 17
Regressions | 2
Score Breakdown
Category | Score | Notes
Performance | 5/10 | FCP 13.8s (improved but still 5.5x target); resources down 70%; APIs fast; /api/home regression 988ms
Security | 3/10 | CSP still weak; HSTS regression on beta; wildcard CORS; localStorage admin vuln remains
Functionality | 6/10 | Deep links fixed; sell form complete; compose works; profile/collection mismatch persists
Ux | 7/10 | Whitespace void fixed; Rp format consistent; clean empty states; minor truncation/grammar issues
Dataintegrity | 3/10 | Grade contradictions; views=0; sold not marked; date mismatches; profile/collection count mismatch
Findings by Severity
Critical | 6
High | 7
Medium | 9
Low | 3
Status Summary
FIXED | 6
IMPROVED | 3
MIXED | 1
NEEDS VERIFICATION | 1
NOT FIXED | 15
NOT TESTED | 2
PARTIALLY FIXED | 1
RESOLVED | 1