## Summary Dashboard
CardVault v13 Audit Summary Dashboard
Audit Version: | v13
Audit Date: | 2026-04-03
Build Version: | v0.81.2 (CVOS)
FINDINGS SUMMARY
Total Findings | 22
Critical | 7
High | 6
Medium | 7
Low | 3
V12 PROGRESSION
Fixed from v12 | 5
Still Open from v12 | 15
New in v13 | 2
Regressions | 2
OVERALL SCORE
Previous (v12): | 5.2
Current (v13): | 5.4
Improvement:
SCORE BREAKDOWN
Performance | 5/10
Security | 4/10
Functionality | 7/10
UX | 7/10
Data Integrity | 3/10

## All Findings
ID | Severity | Category | Title | Description | v12 Ref | Status | Recommendation
V13-001 | Critical | Performance | /api/home response time 2,115ms — 37x regression from v11 baseline | The /api/home endpoint now takes 2,115ms, far exceeding the 500ms target. This has worsened in every version: 56ms (v11) → 988ms (v12) → 2,115ms (v13). The endpoint is likely accumulating more data processing or unoptimized queries with each release. | V12-019 | WORSENED | URGENT: Profile /api/home with server-side APM. Add Redis caching layer. Paginate data response. Consider splitting into multiple lighter endpoints. The 56ms v11 baseline proves this should be fast.
V13-002 | Critical | Security | Admin role still stored in localStorage — privilege escalation possible | cardvault-auth-storage contains isAdmin:true, userRole:ADMIN. cardvault_user contains admin flags. cv_session token in localStorage. Any user can set these via DevTools for admin access. | V12-002 | NOT FIXED | Move all auth state to httpOnly cookies. Server-side JWT authorization. Admin endpoints must verify role server-side. Remove client-side role trust.
V13-003 | Critical | Security | Wildcard CORS: Access-Control-Allow-Origin: * on both domains | Both beta.cardvault.id and admin.cardvault.id return Access-Control-Allow-Origin: *. Allows any website to make requests to CardVault APIs. | V12-003 | NOT FIXED | Restrict CORS to ['https://beta.cardvault.id', 'https://admin.cardvault.id']. Never wildcard with credentialed requests.
V13-004 | Critical | Security | CSP still uses unsafe-eval and unsafe-inline for scripts | script-src still includes 'unsafe-eval' 'unsafe-inline'. IMPROVED: CSP now includes object-src 'none', base-uri 'self', form-action 'self', frame-ancestors 'none' — these are good additions. But core XSS protection remains neutered. | V12-004 | PARTIALLY IMPROVED | Replace unsafe-inline with nonce-based CSP. Eliminate eval() usage. Use strict-dynamic. The new directives (object-src, base-uri, etc.) are a good step — now tackle the script-src.
V13-005 | Critical | Security | HSTS STILL removed from beta.cardvault.id — persistent regression since v12 | Strict-Transport-Security is STILL missing on beta.cardvault.id. This was present in v11, removed in v12, and remains missing in v13. Admin has HSTS correctly configured. The consumer-facing app remains vulnerable to SSL stripping. | V12-005 | NOT FIXED (2nd version) | URGENT: Add HSTS to beta.cardvault.id. Check Vercel headers config — likely admin config was added but beta config is missing or overridden.
V13-006 | Critical | Data Integrity | Profile shows '2 Cards' but My Collection shows '0 total cards' | Profile page shows 2 Cards, sidebar badge shows 2, but My Collection shows '0 total cards' with empty state. All tabs (Collection 0, Listed 0, In Transaction 0, Sold 0) show zero. | V12-006 | NOT FIXED | Debug the /cards API endpoint used by My Collection. It returns empty while Profile/sidebar use correct count. Check for query filter mismatch.
V13-007 | Critical | Performance | FCP 3,812ms — still 1.5x above 2,500ms target | First Contentful Paint at 3,812ms. MASSIVE improvement from v12's 13,812ms (-72%), but still exceeds the 2,500ms target. Resources stable at 18. The improvement suggests prior render-blocking issues were partially addressed. | V12-001 | IMPROVED (still failing) | Close to target now. Profile remaining render-blocking JS. Inline critical CSS. Consider prerender/SSG for Home page. Target: < 2,500ms.
V13-008 | High | Performance | /api/listings/{id} takes 3,040ms — new performance issue | Individual listing API endpoint takes over 3 seconds to respond. This makes card detail pages very slow, especially on deep link navigation where TTFB reaches 2,428ms. | NEW | NEW | Profile the listing detail endpoint. Add server-side caching (Redis). Check for N+1 queries. Pre-compute listing data. Target: < 500ms.
V13-009 | High | Data Integrity | Grade badge contradicts slab — PSA 9 badge vs GEM MINT 10 on slab | Charizard: badge shows PSA 9, slab reads 'PSA GRADED GEM MINT 10'. Blue-Eyes: badge shows 'BGS 9.5' but slab is from CGC. Black Lotus: badge shows 'SCG 9' but slab shows UGA grading authority. | V12-007 | NOT FIXED | Make grade badges dynamic. Read grade value AND company from card data. Validate against slab image data.
V13-010 | High | Data Integrity | Completed transaction listing still shows 'active' status | Transaction #0906f312 is 'Completed' but all associated listings still show 'active' in admin Listings page. The Sold status filter exists but is never triggered by completed transactions. | V12-010 | NOT FIXED | Wire transaction completion event to listing status update. Add post-transaction webhook.
V13-011 | High | Data Integrity | Transaction date inconsistent across admin pages — 3 different formats | Same transaction #0906f312: Transactions page '03 Apr 2026' (improved from v12), Financials page '1 Apr 26', Listings page '3 Apr'. Three different formats AND potentially different dates (Apr 3 vs Apr 1). Dashboard shows no date. | V12-011 | PARTIALLY IMPROVED | Standardize all admin pages on one format: 'DD MMM YYYY'. More critically, verify the transaction date is consistent in the database.
V13-012 | High | Security | No KYC enforcement for high-value transactions | John Collector (UNVERIFIED) completed Rp 25,000,000 transaction. KYC should be required for transactions above Rp 10,000,000. | V12-012 | NOT FIXED | Implement KYC check in transaction flow. Block transactions > Rp 10M for unverified users.
V13-013 | High | UX | Card title truncation on Explore without tooltip | 'Shohei Ohtani Chrome R...' truncated without ellipsis styling or hover tooltip showing full name. | V12-013 | NOT FIXED | Add text-overflow: ellipsis with title attribute. Or allow 2-line wrap.
V13-014 | Medium | Data Integrity | Year field empty, Cert # shows 'N/A' for graded cards | Charizard detail: Year empty, Cert # 'N/A'. Slab clearly shows 1999 and cert numbers 73215846/90001234. | V12-014 | NOT FIXED | Populate Year and Cert # from grading data. Add as required fields when condition is 'Graded'.
V13-015 | Medium | Data Integrity | Collection Value 'Rp 0' despite owning listed cards | Profile shows Rp 0 Collection Value. TokyoCards has 2 active listings worth Rp 60.5M total. | V12-015 | NOT FIXED | Calculate collection value by summing owned/listed card values.
V13-016 | Medium | UX | '1 trades' grammar error — missing singular form | Profile shows '1 trades' in both subtitle and stats section. | V12-016 | NOT FIXED | count === 1 ? 'trade' : 'trades'. Audit all count labels.
V13-017 | Medium | UX | Dashboard label 'Platform Fees (Revenue)' still ambiguous | Dashboard shows 'PLATFORM FEES (REVENUE)' while Financials correctly labels 'Total Platform Revenue'. | V12-017 | NOT FIXED | Change to 'Platform Fees' to match Financials page.
V13-018 | Medium | UX | Admin price format inconsistency — commas vs periods | Transactions page: 'Rp 25,000,000' (commas). Dashboard/Listings/Financials: 'Rp 25.000.000' (periods). Consumer app consistently uses periods. | V12-018 | NOT FIXED | Standardize admin Transactions page on period separators to match Indonesian convention.
V13-019 | Medium | UX | Chart Y-axis 'Volume (IDR)' without Rp formatting | Financials Transaction Volume Trend chart Y-axis uses 'Volume (IDR)' instead of Rp prefix convention. | V12-022 | NOT FIXED | Format chart axis with Rp prefix and abbreviated numbers.
V13-020 | Low | UX | Home page shows no marketplace content — reduced discoverability | Home page only shows hero carousel and CTA. No featured cards, sellers, or recent listings. | V12-023 | NOT FIXED | Add 'Recently Listed' or 'Featured Cards' section to drive engagement.
V13-021 | Low | Operations | Build version v0.81.2 — still not proper semver | Improved from v0.81 to v0.81.2, moving toward semver format. But still not standard MAJOR.MINOR.PATCH. | V12-024 | IMPROVED | Adopt full semver: v0.81.2 → v0.82.0 for next release. Or v1.0.0-rc.1 for pre-release.
V13-022 | Low | Functionality | Sell form validation not tested — submit behavior unknown | Form has required field markers (* on Card Name, Category, Year). Validation behavior on empty required fields needs verification. | V12-025 | NEEDS VERIFICATION | Test form submission with empty required fields. Verify inline error messages appear.

## v12 vs v13 Comparison
v12 ID | Issue | v13 Status | Notes
V12-001 | FCP 13,812ms | IMPROVED | Down to 3,812ms (-72%) — massive improvement but still 1.5x above 2,500ms target
V12-002 | Admin role in localStorage | NOT FIXED | isAdmin:true + cv_session still in localStorage
V12-003 | Wildcard CORS * | NOT FIXED | Still * on both domains
V12-004 | CSP unsafe-eval/unsafe-inline | PARTIALLY IMPROVED | Added object-src 'none', base-uri 'self', form-action 'self', frame-ancestors 'none'. Script-src still unsafe.
V12-005 | HSTS missing from beta | NOT FIXED | Still missing on beta. Admin HSTS maintained.
V12-006 | Profile vs My Collection mismatch | NOT FIXED | Profile shows 2 Cards, My Collection shows 0
V12-007 | Grade badge contradicts slab | NOT FIXED | PSA 9 vs GEM MINT 10, BGS 9.5 vs CGC, SCG 9 vs UGA
V12-008 | Double separator · · | FIXED | Now shows 'Charizard · Base Set' — single separator
V12-009 | All listing views = 0 | FIXED | View tracking implemented! POST /api/listings/{id}/views working. Charizard shows 3 views in admin.
V12-010 | Sold listing still active | NOT FIXED | Completed transaction listing still shows active
V12-011 | Date format inconsistency | PARTIALLY IMPROVED | Transactions now shows '03 Apr 2026' (better). But Financials '1 Apr 26', Listings '3 Apr'. Still 3 different formats.
V12-012 | KYC for high-value tx | NOT FIXED | John Collector UNVERIFIED completed Rp 25M tx
V12-013 | Card title truncation | NOT FIXED | Shohei Ohtani Chrome R... still truncated
V12-014 | Year and Cert # empty | NOT FIXED | Year empty, Cert# N/A. Slab shows 1999 + cert numbers.
V12-015 | Collection Value Rp 0 | NOT FIXED | Rp 0 despite Rp 60.5M in listed cards
V12-016 | '1 trades' grammar | NOT FIXED | Still '1 trades' on Profile
V12-017 | Dashboard revenue label | NOT FIXED | Still 'PLATFORM FEES (REVENUE)'
V12-018 | Admin price commas vs periods | NOT FIXED | Transactions still uses commas while others use periods
V12-019 | /api/home 988ms | WORSENED | Now 2,115ms — further regression from 988ms. 37x worse than v11 baseline of 56ms.
V12-020 | /api/notifications duplicate calls | FIXED | Now 1 call on Explore (was 2 in v12)
V12-021 | Bottom nav Explore broken | FIXED | SPA navigation from Home → Explore now works
V12-022 | Chart Y-axis IDR format | NOT FIXED | Still 'Volume (IDR)'
V12-023 | Home no marketplace content | NOT FIXED | Still only hero + CTA
V12-024 | Version numbering | IMPROVED | v0.81 → v0.81.2. Moving toward semver.
V12-025 | Sell form validation | NEEDS VERIFICATION | Required markers visible (* on fields). Behavior untested.

## Test Cases
TC ID | Area | Scenario | Steps | Expected Result | Priority
TC-001 | Performance | Verify FCP on fresh page load | 1. Clear cache and cookies 2. Open beta.cardvault.id in incognito 3. Measure FCP via Lighthouse 4. Record timing | FCP < 2,500ms | Critical
TC-002 | Performance | Verify /api/home response time | 1. Open DevTools Network tab 2. Hard refresh Home page 3. Check /api/home duration | < 500ms (restore v11 baseline of 56ms) | Critical
TC-003 | Performance | Verify /api/listings/{id} response time | 1. Open DevTools Network 2. Navigate to any card detail 3. Check /api/listings/{id} duration | < 500ms (currently 3,040ms) | Critical
TC-006 | Security | Verify admin role cannot be spoofed via localStorage | 1. Log in as regular user 2. Set localStorage isAdmin=true, userRole=ADMIN 3. Refresh 4. Try admin.cardvault.id/admin | Admin access DENIED. Server returns 403. | Critical
TC-007 | Security | Verify CSP without unsafe directives | 1. Check Content-Security-Policy header 2. Verify no unsafe-eval or unsafe-inline in script-src | Nonce-based CSP. No unsafe-eval/unsafe-inline. | Critical
TC-008 | Security | Verify HSTS on BOTH domains | 1. curl -I https://beta.cardvault.id 2. curl -I https://admin.cardvault.id 3. Check Strict-Transport-Security | HSTS present on BOTH with max-age=31536000; includeSubDomains; preload | Critical
TC-009 | Security | Verify CORS not wildcard | 1. Check Access-Control-Allow-Origin header on both domains 2. Test with foreign origin header | Specific origins only, NOT * | Critical
TC-015 | Data Integrity | Verify Profile card count matches My Collection | 1. Note Profile card count 2. Go to My Collection 3. Compare total cards | Both show same count | Critical
TC-004 | Performance | Verify card detail TTFB on deep link | 1. Copy card detail URL 2. Open in new incognito tab 3. Measure TTFB via Navigation Timing API | TTFB < 800ms (currently 2,428ms) | High
TC-010 | Security | Verify KYC for high-value transactions | 1. Create unverified user 2. Attempt transaction > Rp 10M 3. Check for KYC gate | Transaction blocked for unverified users above Rp 10M | High
TC-011 | Functionality | Verify card detail deep link | 1. Copy card URL from Explore 2. Open in new incognito tab | Card detail loads correctly without redirect | High
TC-012 | Functionality | Verify Sell form price field and List for Sale toggle | 1. Go to Sell/Add Card 2. Toggle 'List for Sale' 3. Check price field and modes | Price field with Rp prefix. Fixed Price and Timed Auction modes work. | High
TC-013 | Functionality | Verify Explore bottom nav works from Home | 1. Navigate to Home 2. Click Explore in bottom nav 3. Check URL changes to /explore | Navigates to /explore and shows listings | High
TC-014 | Functionality | Verify Sell form validation on empty submit | 1. Go to Add New Card 2. Leave required fields empty 3. Click Add to Collection 4. Check for error messages | Inline errors below empty required fields. Form blocked. | High
TC-016 | Data Integrity | Verify grade badge matches slab for all cards | 1. Open each graded card 2. Compare badge text to slab grade 3. Compare badge company to slab company | Badge grade AND company match slab exactly | High
TC-017 | Data Integrity | Verify sold listings marked correctly | 1. Complete a transaction 2. Check listing status in Admin | Status changes from 'active' to 'sold' | High
TC-019 | Data Integrity | Verify transaction date consistency across admin | 1. Check date on Transactions page 2. Check date on Financials page 3. Check Listings date 4. Compare all | Same date value AND same format across all admin pages | High
TC-005 | Performance | Verify /api/notifications single call per nav | 1. Open DevTools Network 2. Navigate between pages 3. Count /api/notifications requests per transition | Exactly 1 call per navigation | Medium
TC-018 | Data Integrity | Verify view counter increments | 1. Note view count in admin Listings 2. Visit card detail on consumer app 3. Check admin view count again | View count incremented by 1 | Medium
TC-020 | Data Integrity | Verify Collection Value calculation | 1. Go to Profile 2. Check Collection Value 3. Sum all owned card values | Collection Value = sum of card values, not Rp 0 | Medium
TC-021 | Data Integrity | Verify Year and Cert # for graded cards | 1. Open graded card detail 2. Check Year field 3. Check Cert # field | Both populated with accurate data from grading cert | Medium
TC-023 | UX | Verify singular/plural grammar | 1. Find user with count = 1 2. Verify singular form used | '1 trade' not '1 trades' | Medium
TC-024 | UX | Verify consistent currency formatting in admin | 1. Check Transactions page prices 2. Check Dashboard prices 3. Check Listings prices 4. Check Financials prices | All use 'Rp XX.XXX.XXX' with period separators | Medium
TC-025 | UX | Verify consistent date formatting in admin | 1. Check date format on Dashboard 2. Transactions 3. Listings 4. Financials | All use 'DD MMM YYYY' format consistently | Medium
TC-026 | UX | Verify card titles not truncated without tooltip | 1. Find card with long name on Explore 2. Check for truncation 3. Hover for tooltip | Full name visible or truncated with ellipsis+tooltip | Medium
TC-029 | Security | Verify CSP new directives maintained | 1. Check CSP header on both domains 2. Verify object-src, base-uri, form-action, frame-ancestors present | object-src 'none'; base-uri 'self'; form-action 'self'; frame-ancestors 'none' | Medium
TC-030 | Performance | Verify /api/listings/{id}/views response time | 1. Navigate to card detail 2. Check POST /api/listings/{id}/views timing in Network tab | < 500ms (currently 760ms) | Medium
TC-022 | UX | Verify no double separators in card subtitles | 1. Open card with populated fields 2. Open card with empty Year 3. Check subtitle format | Clean single separator in all cases | Low
TC-027 | UX | Verify Home page has marketplace content | 1. Navigate to Home 2. Check for featured cards or recent listings below hero | At least some featured/recent listings for engagement | Low
TC-028 | Performance | Verify no whitespace void below content | 1. Scroll to bottom of each page 2. Check for blank scrollable area | No scrollable whitespace below content | Low

## Performance Benchmark
Page | Metric | v12 Value | v13 Value | Target | Status | Change
Home | FCP | 13,812ms | 3,812ms | < 2,500ms | IMPROVED (STILL FAIL) | -72%
Home | TTFB | 70ms | 75ms | < 800ms | PASS | +7%
Home | Load Complete | 250ms | 428ms | < 3,000ms | PASS | +71%
Home | Resources Loaded | 18 | 18 | < 50 | PASS | 0%
Home | /api/home | 988ms | 2,115ms | < 500ms | FAIL (WORSENED) | +114% REGRESSION
Home | /api/exchange-rate | 348ms | 330ms | < 500ms | PASS | -5%
Home | /api/auth/me | 289ms | 333ms | < 500ms | PASS | +15%
Home | /api/auth/session | 275ms | 388ms | < 500ms | PASS | +41%
Home | /api/notifications | 1 call (315ms) | 1 call (333ms) | 1 call | PASS | Stable
Explore | SPA Nav from Home | BROKEN | Works | Bottom nav works | FIXED | FIXED
Explore | /api/listings | < 1s | < 1s | < 1,000ms | PASS | Stable
Explore | /api/notifications calls | 2 | 1 | 1 call | FIXED | FIXED
Card Detail | Deep link nav | Works | Works | Direct access | PASS | Maintained
Card Detail | /api/listings/{id} | N/A | 3,040ms | < 1,000ms | FAIL (NEW) | NEW — very slow
Card Detail | /api/listings/{id}/views | N/A (not implemented) | 760ms | < 500ms | NEAR (NEW) | NEW — view tracking implemented
Card Detail | TTFB (deep link) | N/A | 2,428ms | < 800ms | FAIL | NEW measurement
Admin Listings | Views counter | 0 (all) | 3 (Charizard) | Accurate counts | FIXED | View tracking works

## Security Headers
Header | Beta Value | Admin Value | Status | Notes
access-control-allow-origin | * | * | PRESENT
content-security-policy | default-src 'self'; script-src 'self' 'unsafe-inline' 'unsafe-eval'; style-src 'self' 'unsafe-inline'; img-src 'self' data: https:; font-src 'self' data:; connect-src 'self' https: wss:; object-src 'none'; base-uri 'self'; form-action 'self'; frame-ancestors 'none'; | default-src 'self'; script-src 'self' 'unsafe-inline' 'unsafe-eval'; style-src 'self' 'unsafe-inline'; img-src 'self' data: https:; font-src 'self' data:; connect-src 'self' https: wss:; object-src 'none'; base-uri 'self'; form-action 'self'; frame-ancestors 'none'; | PRESENT
permissions-policy | camera=(), microphone=(), geolocation=(), payment=(self) | camera=(), microphone=(), geolocation=(), payment=(self) | PRESENT
referrer-policy | strict-origin-when-cross-origin | strict-origin-when-cross-origin | PRESENT
strict-transport-security | MISSING (STILL REGRESSION from v11) | max-age=31536000; includeSubDomains; preload | MISSING | Missing from beta domain
x-content-type-options | nosniff | nosniff | PRESENT
x-frame-options | DENY | DENY | PRESENT
x-xss-protection | 1; mode=block | 1; mode=block | PRESENT