## All Findings
ID | Severity | Category | Description | Evidence | Status | Fix Recommendation | Priority
V13-002 | CRITICAL | Functional | Admin role in localStorage | cardvault-auth-storage has isAdmin:true, userRole:ADMIN. cv_session in localStorage. | OPEN | Fix in v15 | HIGH
V13-008 | HIGH | Functional | /api/listings/{id} slow |  | OPEN | Fix in v15 | HIGH
V13-009 | HIGH | Functional | Grade badge contradicts slab | Black Lotus: badge UGA 9 vs slab GEM MT 10. Ohtani card shows Aaron Judge image entirely. | PARTIAL | Fix in v15 | HIGH
V13-010 | HIGH | Functional | Completed transaction listing still active | Transaction completed but listing shows active in admin | OPEN | Fix in v15 | HIGH
V13-011 | HIGH | Functional | Date format inconsistent | Transactions: 03 Apr 2026. Financials: 01 Apr 2026 for same transaction. | OPEN | Fix in v15 | HIGH
V13-012 | HIGH | Functional | No KYC enforcement for high-value transactions | John Collector is UNVERIFIED but has Rp 25M transaction | UNVERIFIED | Fix in v15 | HIGH
V13-013 | HIGH | Functional | Card title truncation without tooltip | Shohei Ohtani Chrome R... no title attribute | OPEN | Fix in v15 | HIGH
V13-014 | MEDIUM | Functional | Year empty + Cert # N/A for graded cards | Year blank, Cert # shows N/A despite slab showing 1999 and cert numbers | OPEN | Fix in v15 | MEDIUM
V13-015 | MEDIUM | Functional | Collection Value Rp 0 | Should sum owned card values | OPEN | Fix in v15 | MEDIUM
V13-016 | MEDIUM | Functional | 1 trades grammar | Profile shows '1 trades' and '1 Trades' | OPEN | Fix in v15 | MEDIUM
V13-017 | MEDIUM | Functional | Dashboard label PLATFORM FEES (REVENUE) | Should be Platform Fees | OPEN | Fix in v15 | MEDIUM
V13-018 | MEDIUM | Functional | Admin price format inconsistent | Transactions uses commas (Rp 25,000,000), Listings/Financials use periods | OPEN | Fix in v15 | MEDIUM
V13-019 | MEDIUM | Functional | Chart Y-axis Volume (IDR) | Should use Rp prefix | OPEN | Fix in v15 | MEDIUM
V13-020 | LOW | Functional | Home page lacks marketplace content | No Recently Listed or Featured Cards section | OPEN | Fix in v15 | MEDIUM
V14-001 | CRITICAL | Performance | FCP regression to 17,656ms | Was 3,812ms in v13, now 17,656ms. 4.6x regression. Resources increased from 18 to 28. | NEW | Investigate root cause | CRITICAL
V14-002 | HIGH | Functional | Card data mismatch — Ohtani listing shows Aaron Judge | Listing titled 'Shohei Ohtani Chrome RC Auto' with subtitle 'Shohei Ohtani' displays an Aaron Judge PSA 10 slab image. Complete card-image mismatch. | NEW | Implement fix | HIGH
V14-003 | MEDIUM | Functional | Build version inconsistency between consumer and admin | Consumer shows CARDVAULT BUILD V0.81, admin shows CVOS v0.81.2. Build version regressed on consumer from v0.81.2 in v13. | NEW | Implement fix | MEDIUM
V14-004 | LOW | Functional | x-powered-by: Next.js header exposes technology | New header in v14 reveals server technology. Remove for security hardening. | NEW | Implement fix | MEDIUM
V14-005 | MEDIUM | Security | CORS on admin returns beta origin only | admin.cardvault.id returns Access-Control-Allow-Origin: https://beta.cardvault.id — should also include admin domain for admin API calls. | NEW | Implement fix | MEDIUM
V14-006 | MEDIUM | Security | style-src still has unsafe-inline in CSP | While script-src was fixed with nonces, style-src still uses 'unsafe-inline'. Should use nonces for styles too. | NEW | Implement fix | MEDIUM
V14-007 | LOW | Functional | V13-021 semver adoption still pending | Consumer shows V0.81 (regression), admin v0.81.2. Neither follows proper semver. | NEW | Implement fix | MEDIUM

## v13 vs v14 Comparison
Finding ID | Description | v13 Status | v14 Status | Change
V13-001 | /api/home response time | OPEN | FIXED | FIXED
V13-003 | Wildcard CORS | OPEN | FIXED | FIXED
V13-004 | CSP unsafe-eval/unsafe-inline | OPEN | FIXED | FIXED
V13-005 | HSTS missing from beta | OPEN | FIXED | FIXED
V13-006 | Profile 2 Cards vs My Collection 0 total | OPEN | FIXED | FIXED
V13-007 | FCP 3,812ms | OPEN | FIXED | REGRESSED
V13-009 | Grade badge contradictions | OPEN | FIXED | PARTIAL
V13-022 | Sell form validation | OPEN | FIXED | PARTIAL
V13-002 | Admin role in localStorage | OPEN | NOT FIXED | UNCHANGED
V13-008 | /api/listings/{id} slow | OPEN | NOT FIXED | UNCHANGED
V13-009 | Grade badge contradicts slab | OPEN | PARTIAL | UNCHANGED
V13-010 | Completed transaction listing still active | OPEN | NOT FIXED | UNCHANGED
V13-011 | Date format inconsistent | OPEN | NOT FIXED | UNCHANGED
V13-012 | No KYC enforcement for high-value transactions | OPEN | UNVERIFIED | UNCHANGED
V13-013 | Card title truncation without tooltip | OPEN | NOT FIXED | UNCHANGED
V13-014 | Year empty + Cert # N/A for graded cards | OPEN | NOT FIXED | UNCHANGED
V13-015 | Collection Value Rp 0 | OPEN | NOT FIXED | UNCHANGED
V13-016 | 1 trades grammar | OPEN | NOT FIXED | UNCHANGED
V13-017 | Dashboard label PLATFORM FEES (REVENUE) | OPEN | NOT FIXED | UNCHANGED
V13-018 | Admin price format inconsistent | OPEN | NOT FIXED | UNCHANGED
V13-019 | Chart Y-axis Volume (IDR) | OPEN | NOT FIXED | UNCHANGED
V13-020 | Home page lacks marketplace content | OPEN | NOT FIXED | UNCHANGED
V14-001 | FCP regression to 17,656ms | N/A | NEW | NEW
V14-002 | Card data mismatch — Ohtani listing shows Aaron Judge | N/A | NEW | NEW
V14-003 | Build version inconsistency between consumer and admin | N/A | NEW | NEW
V14-004 | x-powered-by: Next.js header exposes technology | N/A | NEW | NEW
V14-005 | CORS on admin returns beta origin only | N/A | NEW | NEW
V14-006 | style-src still has unsafe-inline in CSP | N/A | NEW | NEW
V14-007 | V13-021 semver adoption still pending | N/A | NEW | NEW

## Test Cases
TC ID | Category | Test Case Title | Preconditions | Steps | Expected Result | Priority | Related Finding
TC-001 | Performance | Verify FCP under 3000ms on home page | Chrome DevTools open, network throttling disabled | 1. Open https://beta.cardvault.id 2. Measure FCP metric 3. Record value | FCP < 3000ms | CRITICAL | V14-001
TC-002 | Performance | Verify /api/home response time < 500ms | Network tab open, cache cleared | 1. Navigate to home page 2. Filter XHR to /api/home 3. Check response time | < 500ms | HIGH | V13-001
TC-003 | Performance | Verify /api/listings/{id} response < 500ms | Card detail page, SPA navigation | 1. Open card listing 2. Navigate to card detail 3. Check /api/listings/{id} timing | < 500ms | HIGH | V13-008
TC-004 | Performance | Verify deep link TTFB under 2000ms | Share card detail deep link | 1. Paste deep link in new tab 2. Measure TTFB 3. Record value | < 2000ms | HIGH | V13-001
TC-005 | Security | Verify localStorage admin bypass prevented | Open admin domain, inspect storage | 1. Navigate to admin.cardvault.id 2. Open DevTools > Storage > localStorage 3. Verify no isAdmin:true found | No admin role in localStorage | CRITICAL | V13-002
TC-006 | Security | Verify CORS restrict to beta domain | Fetch from different origin | 1. Open DevTools > Network 2. Trigger API call 3. Check Access-Control-Allow-Origin header | Header = https://beta.cardvault.id only | CRITICAL | V13-003
TC-007 | Security | Verify CSP nonce on script tags | Inspect page source | 1. Open DevTools > Elements 2. Find <script> tags 3. Verify nonce attribute present | All scripts have nonce-xxx attribute | CRITICAL | V13-004
TC-008 | Security | Verify HSTS header present on both domains | Check response headers | 1. Open Network tab 2. Check response headers for HSTS 3. Verify max-age=31536000 | HSTS present, max-age=31536000 | CRITICAL | V13-005
TC-009 | Functionality | Verify grade badge accuracy for Black Lotus | Profile page with graded cards | 1. View Profile 2 2. Find Black Lotus card 3. Compare badge to slab | Badge UGA 9 matches slab GEM MT 10 | HIGH | V13-009
TC-010 | Functionality | Verify correct card image for Ohtani listing | Card detail page | 1. Find Shohei Ohtani Chrome RC listing 2. Verify image 3. Confirm not Aaron Judge | Correct Ohtani card image displayed | HIGH | V14-002
TC-011 | Functionality | Verify sold transaction marked inactive in admin | Admin listings view | 1. Find completed transaction 2. Check admin listing status 3. Verify marked as inactive | Status = inactive | HIGH | V13-010
TC-012 | Functionality | Verify date format consistency across pages | Transactions and financials pages | 1. View transaction date 2. View financial date for same transaction 3. Compare formats | Both show "03 Apr 2026" format | HIGH | V13-011
TC-013 | Functionality | Verify My Collection card count accurate | My Collection page | 1. Navigate to My Collection 2. Count cards displayed 3. Verify matches header total | Count matches header (2 cards) | HIGH | V13-006
TC-014 | Functionality | Verify collection value calculated correctly | My Collection page | 1. Sum owned card values 2. Compare to collection value 3. Verify calculation | Collection value = sum of card values | MEDIUM | V13-015
TC-015 | UX | Verify card title truncation has tooltip | Card detail view | 1. Hover over truncated title 2. Check for tooltip 3. Verify full title appears | Tooltip shows full title | MEDIUM | V13-013
TC-016 | UX | Verify subtitle separator format | Card detail page | 1. View card details 2. Check subtitle formatting 3. Verify "Card Name · Set Name" | Format: "Shohei Ohtani · Topps Chrome" | MEDIUM | V12-008
TC-017 | UX | Verify grammar for single trade | Profile page | 1. View user with 1 trade 2. Check label text 3. Verify singular form | Shows "1 trade" not "1 trades" | MEDIUM | V13-016
TC-018 | UX | Verify currency format consistency in admin | Admin dashboard transactions | 1. View transaction amounts 2. Check formatting 3. Verify Rp prefix and delimiter | Consistent format: Rp 25,000,000 | MEDIUM | V13-018
TC-019 | UX | Verify year field not empty for graded cards | Card detail page | 1. Find graded card (Black Lotus) 2. Check year field 3. Verify not blank | Year = 1999 | MEDIUM | V13-014
TC-020 | UX | Verify form validation shows error messages | Sell form | 1. Click sell button 2. Submit without required fields 3. Check for error text | Error messages visible on required fields | MEDIUM | V13-022
TC-021 | Regression | Verify view count tracking still works | Card detail, admin | 1. View card detail multiple times 2. Check admin view count 3. Verify increments | View count = 5 for Charizard | MEDIUM | V12-009
TC-022 | Regression | Verify notifications deduplicated | Home page navigation | 1. Navigate between pages 2. Monitor /api/notifications calls 3. Count requests | Single /api/notifications call per nav | LOW | V12-020
TC-023 | Regression | Verify bottom nav Explore works from Home | Home page | 1. Click Explore in bottom nav 2. Verify navigation 3. Check URL change | Navigates to Explore (/explore) | LOW | V12-021
TC-024 | Regression | Verify card detail deep links functional | Share card detail link | 1. Copy card deep link 2. Open in new tab 3. Verify card loads | Card detail page loads correctly | MEDIUM | V12-008
TC-025 | Regression | Verify Messages compose icon works | Messages page | 1. Click compose icon 2. Verify modal opens 3. Check form fields appear | Compose modal opens with form | LOW | V12-021
TC-026 | Security | Verify x-powered-by header not exposed | Response headers | 1. Check response headers 2. Look for x-powered-by 3. Verify removed or obfuscated | x-powered-by header absent | LOW | V14-004
TC-027 | Security | Verify admin CORS allows admin domain | Admin API calls | 1. Call API from admin.cardvault.id 2. Check CORS header 3. Verify admin domain included | CORS header includes admin domain | MEDIUM | V14-005
TC-028 | Security | Verify CSP style-src uses nonces | Page source inspection | 1. Inspect <style> tags 2. Verify nonce attributes 3. Check no unsafe-inline | All styles use nonces, no unsafe-inline | MEDIUM | V14-006
TC-029 | Functionality | Verify KYC enforcement for high-value transactions | Admin transaction approval | 1. Check user verification status 2. Attempt Rp 25M transaction 3. Verify KYC required | KYC verification enforced | HIGH | V13-012
TC-030 | Functionality | Verify certification number displays correctly | Card detail page | 1. View graded card details 2. Check Cert # field 3. Verify not showing N/A | Cert # displays actual cert number | MEDIUM | V13-014

## Performance Benchmark
Metric | v13 Value (ms) | v14 Value (ms) | Target (ms) | Status | Change | Notes
FCP (First Contentful Paint) | 3812 | 17656 | 3000 | FAIL | +4.6x regression | Resource count increased from 18 to 28
Home Page TTFB | N/A | 755 | 800 | PASS | New | Time to First Byte
Load Complete | N/A | 1056 | 2000 | PASS | New | Full page load time
/api/home | 2115 | 342 | 500 | PASS | -83.8% | Major improvement
/api/listings/{id} (SPA) | 3040 | 2227 | 500 | FAIL | -26.8% | Still well over target
/api/listings/{id} (cached) | N/A | 2950 | 500 | FAIL | New | Deep link TTFB route
/api/views | N/A | 1128 | 800 | FAIL | New | SPA navigation performance
/api/exchange-rate | N/A | 568 | 600 | FAIL | New | Currency conversion API
/api/auth/me | N/A | 329 | 500 | PASS | New | User info endpoint
/api/auth/session | N/A | 306 | 500 | PASS | New | Session management
/api/notifications | N/A | 322 | 500 | PASS | New | Notification endpoint
Deep Link TTFB | N/A | 2442 | 2000 | FAIL | New | Cold page load for shared links
DOM Complete (deep link) | N/A | 2747 | 2000 | FAIL | New | DOM ready time
Resource Count (home) | 18 | 28 | 20 | FAIL | +55% | Resource bloat detected

## Security Headers
Header | Beta Value | Admin Value | Expected Value | Status
HSTS | max-age=31536000; includeSubDomains; preload | max-age=31536000; includeSubDomains; preload | max-age >= 31536000 | PASS
CSP script-src | 'self' 'nonce-xxx' 'strict-dynamic' | 'self' 'nonce-xxx' 'strict-dynamic' | 'self' nonce 'strict-dynamic' | PASS
CSP style-src | 'self' 'unsafe-inline' | 'self' 'unsafe-inline' | 'self' with nonces (no unsafe-inline) | PARTIAL
CSP img-src | 'self' data: https: | 'self' data: https: | 'self' https: (allow data: for base64) | PASS
CORS (Allow-Origin) | https://beta.cardvault.id | https://beta.cardvault.id | Should include admin for admin APIs | PARTIAL
X-Frame-Options | DENY | DENY | DENY | PASS
X-Content-Type-Options | nosniff | nosniff | nosniff | PASS
X-XSS-Protection | 1; mode=block | 1; mode=block | 1; mode=block | PASS
Permissions-Policy | camera=(), microphone=(), geolocation=() | camera=(), microphone=(), geolocation=() | Restrict unnecessary APIs | PASS
Referrer-Policy | strict-origin-when-cross-origin | strict-origin-when-cross-origin | strict-origin-when-cross-origin | PASS
x-powered-by | Next.js | Next.js | Not exposed or removed | FAIL
Cache-Control | private, no-cache, no-store | Not listed | no-store for auth pages | PARTIAL

## Summary Dashboard
CardVault v14 Audit Summary
OVERALL METRICS
Audit Date | 2026-04-03
Overall Score | 6.2 / 10
Previous Score (v13) | 5.4 / 10
Score Improvement | +0.8 points (+14.8%)
FINDINGS BY SEVERITY
CRITICAL | 3
HIGH | 6
MEDIUM | 9
LOW | 3
SCORE BREAKDOWN
Performance | 4.5 | Weight: 25%
Security | 7.5 | Weight: 25%
Functionality | 6 | Weight: 20%
UX | 6.5 | Weight: 15%
Data Integrity | 5.5 | Weight: 15%
DEPLOYMENT READINESS
Critical Issues Blocking Deployment | 3 | FCP regression, admin role bypass, incorrect images
Security Status | IMPROVED | HSTS, CORS, CSP nonces fixed; style-src still needs work
Performance Status | REGRESSED | FCP increased 4.6x; API improvements offset by resource bloat
Recommendation | NOT READY | Address FCP regression, card image mismatch, and admin role in storage
KEY IMPROVEMENTS (v13 -> v14)
• /api/home: 2,115ms -> 342ms (-83.8%)
• Wildcard CORS fixed to beta domain only
• CSP script-src now uses nonces + strict-dynamic
• HSTS added to beta domain
• My Collection card count: 0 -> 2 cards
• Form validation visual improvements
CRITICAL REGRESSIONS
• FCP: 3,812ms -> 17,656ms (+4.6x) — BLOCKING
• Card image mismatch: Ohtani shows Aaron Judge
• Grade badge contradictions persist on some cards
• Admin role still stored in localStorage