## All Findings
ID | Pillar | Category | Title | Description | Severity | Impact | Effort | Priority | Status | Recommendation
CVA-V21-001 | Functional | Authentication | Google OAuth Sign-In Failure | Clicking "Continue with Google" returns error=OAuthSignin in URL but no error message displayed to user | HIGH | Users cannot sign in via Google | Quick Win (1-2hrs) | P1 - Critical | Open | Check Google OAuth client configuration, add visible error handling
CVA-V21-002 | Security | API Auth | Beta /api/listings Unauthenticated Access | GET /api/listings returns 200 with full listing data including seller PII without authentication | MEDIUM | Data exposure, inconsistent auth | Quick Win (1hr) | P2 - High | Open | Add auth middleware to /api/listings or strip sensitive fields
CVA-V21-003 | UX | Navigation | Admin 404 Pages Break Layout | Direct navigation to /dashboard or /kyc-approvals returns default 404 with no sidebar | MEDIUM | Admin users lose navigation context | Moderate (1 day) | P2 - High | Open | Implement custom 404 within admin layout
CVA-V21-004 | Performance | TTFB | Beta Cold-Start TTFB Regression | First-visit TTFB at 2,593ms vs 350ms warm (target <800ms) | MEDIUM | First visitors wait 2.6s for content | Moderate (2-3 days) | P3 - Medium | Open | Vercel cron warming, Edge Runtime for landing
CVA-V21-005 | Security | Info Disclosure | Build Version Exposed in UI | v0.9.0 shown in top-right of both sites, admin footer | LOW | Minor info disclosure | Quick Win (30min) | P4 - Low | Open | Remove or genericize version in production
CVA-V21-006 | Security | Info Disclosure | Admin Email in Sidebar | Logged-in email shown in plain text in sidebar | LOW | Minor info exposure | Quick Win (30min) | P4 - Low | Open | Truncate email or show display name

## V20 Resolution Status
Original ID | Title | V20 Severity | V21 Status | Resolution Notes
CVA-001 | Admin Zero Authentication | CRITICAL | RESOLVED | All API endpoints return 401. All routes redirect. KYC adds OTP.
CVA-002 | Broken Card Images (50%) | HIGH | CANNOT VERIFY | OAuth failure prevents marketplace access
CVA-003 | Missing HSTS on Beta | HIGH | RESOLVED | HSTS active: max-age=31536000; includeSubDomains; preload
CVA-004 | Admin FCP >10,000ms | HIGH | PARTIALLY RESOLVED | Full load improved to 905ms, FCP still above target
CVA-005 | Notification 401 Spam | MEDIUM | RESOLVED | Zero console errors, no unauth API calls
CVA-006 | Beta HEAD Returns 503 | MEDIUM | RESOLVED | Beta responds normally
CVA-007 | Build Version Exposed | LOW | NOT RESOLVED | v0.9.0 still visible in both sites
CVA-008 | Cache-Control Public | LOW | RESOLVED | Now private, no-cache, no-store

## Quick Wins
ID | Pillar | Category | Title | Description | Severity | Impact | Effort | Priority | Status | Recommendation
CVA-V21-001 | Functional | Authentication | Google OAuth Sign-In Failure | Clicking "Continue with Google" returns error=OAuthSignin in URL but no error message displayed to user | HIGH | Users cannot sign in via Google | Quick Win (1-2hrs) | P1 - Critical | Open | Check Google OAuth client configuration, add visible error handling
CVA-V21-002 | Security | API Auth | Beta /api/listings Unauthenticated Access | GET /api/listings returns 200 with full listing data including seller PII without authentication | MEDIUM | Data exposure, inconsistent auth | Quick Win (1hr) | P2 - High | Open | Add auth middleware to /api/listings or strip sensitive fields
CVA-V21-005 | Security | Info Disclosure | Build Version Exposed in UI | v0.9.0 shown in top-right of both sites, admin footer | LOW | Minor info disclosure | Quick Win (30min) | P4 - Low | Open | Remove or genericize version in production
CVA-V21-006 | Security | Info Disclosure | Admin Email in Sidebar | Logged-in email shown in plain text in sidebar | LOW | Minor info exposure | Quick Win (30min) | P4 - Low | Open | Truncate email or show display name

## Summary Dashboard
CARDVAULT V21 AUDIT - SUMMARY DASHBOARD
Findings by Severity
HIGH | 1
MEDIUM | 3
LOW | 2
Findings by Pillar
Functional | 1
Performance | 1
Security | 3
UX | 1
V20 Resolution Rate
Fully Resolved: 6/8 (75%)
Partially Resolved: 1/8 (12.5%)
Not Resolved: 1/8 (12.5%)
Overall Audit Score
7.6 / 10.0