## Findings Tracker
ID | Finding | Severity | Category | Status | V21 Status | V22 Status | Owner | Due Date | Notes
CVA-V21-001 | Google OAuth Error Handling | HIGH | Functional | Closed | OPEN | FIXED | Frontend Team | 2026-04-01 | Red error banner now visible on auth failure
CVA-V21-002 | /api/listings PII Data Leak | HIGH | Security | Closed | OPEN | FIXED | Backend Team | 2026-04-01 | Returns 401 without session, cookies() validation added
CVA-V21-003 | Admin 404 Layout Break | MEDIUM | UX | Closed | OPEN | FIXED | Frontend Team | 2026-04-02 | catch-all route preserves sidebar layout
CVA-V21-004 | Beta TTFB Cold-Start | MEDIUM | Performance | Closed | OPEN | FIXED | DevOps Team | 2026-04-03 | Cron warming + Edge Runtime, 305ms warm TTFB
CVA-V21-005 | Version Number Exposed | LOW | Security | Open | OPEN | NOT FIXED | Frontend Team | 2026-04-10 | v0.9.0 visible top-right both sites
CVA-V21-006 | Admin Email in Sidebar | LOW | UX | Open | OPEN | NOT FIXED | Frontend Team | 2026-04-10 | Email plaintext in admin sidebar

## Summary
Findings Summary
Total Findings:
Findings Status
Open
Closed
By Severity
HIGH
MEDIUM
LOW
Fix Rate